## Cover
RESOLUTE COMPLIANCE ADVISORY LLP
Governance · Risk · Compliance
CORRECTIVE ACTION PLAN
NCA ECC-1:2018 + SAMA CSF ¦ Al Ameen Insurance Company
Document Reference | RCA-P3-005
Client | Al Ameen Insurance Company
Engagement | NCA ECC-1:2018 + SAMA CSF Compliance Audit
Prepared by | kay Shahbaaz — GRC Auditor
Reviewed by | Resolute Compliance Advisory LLP
Audit Period | 15 July 2024 – 31 October 2024
CAP Period | November 2024 – October 2025
Date Issued | 31 October 2024
Version | v1.0
Classification | CONFIDENTIAL
REMEDIATION PHASES — 30 CORRECTIVE ACTIONS
Phase 1 — Nov–Dec 2024 | Critical governance & live risks — CISO, shared credentials, third-party access, log retention
Phase 2 — Jan–Mar 2025 | Risk management, incident response, log management, awareness training, policy framework
Phase 3 — Apr–Jun 2025 | Third-party contracts, vulnerability management, BCP/DR framework, backup capability
Phase 4 — Jul–Oct 2025 | BCP/DR testing, SAMA CSF maturity validation, audit readiness

## Corrective Action Plan
Action ID | Phase | Period | Action Title | Detail | Priority | Finding Ref | Risk Ref | Owner | Start Date | Target Date | Effort (Days) | Status | Completion Date | Evidence
PHASE 1 — NOVEMBER–DECEMBER 2024 — CRITICAL GOVERNANCE & LIVE RISKS
CA-001 | 1 | Nov–Dec 2024 | Appoint CISO or designate cybersecurity accountable person | Create and fill a CISO role or formally designate a named cybersecurity accountable person at senior management level with a defined mandate, authority, and direct Board/CEO reporting line. All subsequent remediation actions depend on this appointment. | Critical | F-001, F-002 | R-001, R-002 | Board / CEO | 01 Nov 2024 | 30 Nov 2024 | 5 | Open
CA-002 | 1 | Nov–Dec 2024 | IMMEDIATE: Disable shared admin account on Oracle Insurance — create individual named accounts | Create individually named administrator accounts for each authorised IT staff member on Oracle Insurance Policy Administration. Disable the shared administrator account immediately. Document all authorised administrator accounts. This is a live risk requiring action within 5 business days of report receipt. | Critical | F-007 | R-006 | IT Operations Manager | 01 Nov 2024 | 07 Nov 2024 | 3 | Open — LIVE
CA-003 | 1 | Nov–Dec 2024 | IMMEDIATE: Rotate all Oracle Insurance administrative credentials | Rotate all administrative credentials on Oracle Insurance Policy Administration following creation of individual named accounts. Ensure no former employees retain credential knowledge. Implement credential rotation schedule — minimum every 90 days for privileged accounts. | Critical | F-007 | R-006 | IT Operations Manager | 07 Nov 2024 | 14 Nov 2024 | 2 | Open — LIVE
CA-004 | 1 | Nov–Dec 2024 | Enable privileged session logging on Oracle Insurance | Configure audit logging for all administrator sessions on Oracle Insurance Policy Administration. Ensure logs capture user ID, timestamp, and actions performed. Integrate with the log retention remediation (CA-014) to ensure logs are retained for 12 months. | Critical | F-007, F-010 | R-006 | IT Operations Manager | 14 Nov 2024 | 30 Nov 2024 | 3 | Open
CA-005 | 1 | Nov–Dec 2024 | Initiate cybersecurity strategy development | Engage the newly appointed CISO to develop a cybersecurity strategy document aligned to NCA ECC-1:2018 and SAMA CSF requirements. Strategy should define objectives, scope, governance structure, and three-year roadmap. Present to Board for approval by end of Phase 1. | Critical | F-001 | R-001 | CISO | 15 Nov 2024 | 31 Dec 2024 | 15 | Open
CA-006 | 1 | Nov–Dec 2024 | Conduct emergency review of Najm, Munich Re, and Swiss Re access rights | Immediately review the scope of system access for Najm (Oracle Insurance integration), Munich Re, and Swiss Re (reinsurance file transfer). Confirm access is restricted to the minimum required. Document current access arrangements as baseline for contractual remediation. | Critical | F-004 | R-011, R-012, R-013 | IT Operations Manager / Legal | 01 Nov 2024 | 30 Nov 2024 | 5 | Open
CA-007 | 1 | Nov–Dec 2024 | Extend audit log retention to 12 months — Azure AD immediate action | As an emergency action, configure Azure AD log retention to 12 months using Log Analytics workspace or Azure AD P1 licence upgrade. This addresses the most accessible log retention gap and the SAMA compliance requirement. Full log centralisation to follow in Phase 2. | Critical | F-010 | R-010 | IT Operations Manager | 01 Nov 2024 | 15 Nov 2024 | 2 | Open
CA-008 | 1 | Nov–Dec 2024 | Conduct user access audit — Oracle Insurance, Guidewire, Azure AD | Audit all active user accounts across Oracle Insurance, Guidewire ClaimCenter, and Azure AD against the current active employee list. Identify and disable orphaned accounts, former employee accounts, and accounts with excessive privileges. Document findings. | High | F-007 | R-007 | IT Operations Manager | 01 Nov 2024 | 30 Nov 2024 | 5 | Open
PHASE 2 — JANUARY–MARCH 2025 — RISK MANAGEMENT, INCIDENT RESPONSE, TRAINING & POLICY
CA-009 | 2 | Jan–Mar 2025 | Develop cybersecurity risk assessment methodology | Document a formal cyber risk assessment methodology defining: scope boundaries, threat source catalogue, likelihood and impact criteria, risk scoring methodology (L×I, 1–25), risk rating bands, and review frequency. Have methodology approved by CISO and senior management. | Critical | F-003 | R-004 | CISO | 06 Jan 2025 | 31 Jan 2025 | 10 | Open
CA-010 | 2 | Jan–Mar 2025 | Conduct organisation-wide cyber risk assessment | Conduct the first formal cyber risk assessment covering all critical systems — Oracle Insurance, Guidewire ClaimCenter, Azure AD, Azure KSA workloads, and all third-party integrations. Produce a formal risk assessment report. Use findings to validate and update RCA-P3-004 risk register. | Critical | F-003 | R-004 | CISO | 01 Feb 2025 | 28 Feb 2025 | 15 | Open
CA-011 | 2 | Jan–Mar 2025 | Develop and implement incident response plan | Develop a cybersecurity incident response plan covering: incident classification and severity matrix; escalation paths and IR team roster; containment, eradication, and recovery procedures; SAMA breach notification procedure and timelines; communication protocols for internal and external stakeholders. Assign named IR plan owner. | High | F-009 | R-009 | CISO | 06 Jan 2025 | 28 Feb 2025 | 15 | Open
CA-012 | 2 | Jan–Mar 2025 | Conduct incident response tabletop exercise | Design and run a tabletop exercise simulating a ransomware incident against Oracle Insurance Policy Administration. Test the IR plan, escalation procedures, and SAMA notification workflow. Document lessons learned and update the IR plan accordingly. | High | F-009 | R-009 | CISO / IT Operations Manager | 01 Mar 2025 | 31 Mar 2025 | 5 | Open
CA-013 | 2 | Jan–Mar 2025 | Extend audit log retention to 12 months — Oracle Insurance and Guidewire | Configure audit log retention to 12 months for Oracle Insurance Policy Administration and Guidewire ClaimCenter. Verify log completeness, integrity controls, and access restrictions. Document configuration as evidence of SAMA CSF compliance. | High | F-010 | R-010 | IT Operations Manager | 06 Jan 2025 | 31 Jan 2025 | 5 | Open
CA-014 | 2 | Jan–Mar 2025 | Implement centralised log management solution | Deploy a centralised log management platform to aggregate logs from Oracle Insurance, Guidewire ClaimCenter, Azure AD, and network devices. Configure log forwarding, define monitoring rules, and establish alert thresholds for key security events including privileged access, authentication failures, and data access anomalies. | High | F-010 | R-010 | IT Operations Manager | 01 Feb 2025 | 31 Mar 2025 | 20 | Open
CA-015 | 2 | Jan–Mar 2025 | Develop and launch mandatory security awareness training programme | Develop a mandatory security awareness training programme covering: phishing and social engineering, data handling and policyholder data protection, password and access control, acceptable use, and incident reporting. Deliver to all 290 staff. Track completion rates and report to management. | High | F-006 | R-003 | CISO / HR | 06 Jan 2025 | 31 Mar 2025 | 15 | Open
CA-016 | 2 | Jan–Mar 2025 | Integrate security awareness into onboarding programme | Update the HR onboarding process to include mandatory security awareness training for all new joiners prior to system access provisioning. Define security awareness as a prerequisite for new joiner access activation. | High | F-006 | R-003 | HR / CISO | 06 Jan 2025 | 28 Feb 2025 | 3 | Open
CA-017 | 2 | Jan–Mar 2025 | Develop cybersecurity policy framework | Develop and obtain senior management approval for a cybersecurity policy framework covering: information security policy, access control policy, privileged access management policy, incident response policy, data classification policy, third-party security policy, and acceptable use policy. | Critical | F-001 | R-001, R-002 | CISO | 06 Jan 2025 | 31 Mar 2025 | 20 | Open
CA-018 | 2 | Jan–Mar 2025 | Define and enforce SAMA breach notification procedure | Document a standalone SAMA breach notification procedure defining: notification trigger criteria, responsible notification owner, SAMA contact details, notification timeline (as required by SAMA regulations), content requirements, and internal escalation path. Integrate with incident response plan. | High | F-009 | R-017 | Compliance / CISO | 06 Jan 2025 | 31 Jan 2025 | 3 | Open
CA-019 | 2 | Jan–Mar 2025 | Implement MFA on Oracle Insurance Policy Administration | Configure multi-factor authentication for all user and administrator access to Oracle Insurance Policy Administration. Align with the access control policy developed in CA-017. Document MFA configuration as evidence. | High | F-007 | R-008 | IT Operations Manager | 01 Feb 2025 | 28 Feb 2025 | 5 | Open
CA-020 | 2 | Jan–Mar 2025 | Establish semi-annual access review cycle | Implement a formal semi-annual access review process for Oracle Insurance, Guidewire ClaimCenter, and Azure AD. Define review scope, responsible reviewer, approval authority, and remediation timeline for identified excess access. Conduct first review as part of this action. | High | F-007 | R-007 | IT Operations Manager / CISO | 01 Mar 2025 | 31 Mar 2025 | 5 | Open
PHASE 3 — APRIL–JUNE 2025 — THIRD-PARTY SECURITY, VULNERABILITY MANAGEMENT & BCP/DR FRAMEWORK
CA-021 | 3 | Apr–Jun 2025 | Develop third-party cybersecurity management policy | Develop and approve a third-party cybersecurity management policy covering: vendor risk tiering criteria, security assessment requirements by tier, minimum contractual security obligations, access control requirements, incident notification obligations, and exit and data destruction requirements. | Critical | F-004 | R-011, R-012, R-013, R-014 | CISO / Legal | 01 Apr 2025 | 30 Apr 2025 | 10 | Open
CA-022 | 3 | Apr–Jun 2025 | Renegotiate Najm contract — add cybersecurity clauses | Engage Legal to renegotiate the Najm contract to include cybersecurity obligations: minimum security standards, assessment rights, incident notification within 24 hours, data handling requirements, and access control obligations. Complete contractual amendment and obtain signed agreement. | Critical | F-004 | R-011 | Legal / CISO | 01 Apr 2025 | 30 Jun 2025 | 10 | Open
CA-023 | 3 | Apr–Jun 2025 | Renegotiate Munich Re and Swiss Re reinsurance agreements — add cybersecurity clauses | Engage Legal to add cybersecurity requirements to Munich Re and Swiss Re reinsurance agreements covering: minimum security standards for file transfer, incident notification obligations, access scope restrictions, and periodic review rights. | Critical | F-004 | R-012, R-013 | Legal / CISO | 01 Apr 2025 | 30 Jun 2025 | 10 | Open
CA-024 | 3 | Apr–Jun 2025 | Conduct security assessments for Najm, Munich Re, and Swiss Re | Conduct security questionnaire-based assessments for Najm, Munich Re, and Swiss Re covering: their cybersecurity programme, access control practices, incident history, data protection controls, and regulatory compliance posture. Document findings and define monitoring cadence. | Critical | F-004 | R-011, R-012, R-013 | CISO | 01 May 2025 | 30 Jun 2025 | 15 | Open
CA-025 | 3 | Apr–Jun 2025 | Implement scheduled vulnerability management programme | Deploy a vulnerability scanning tool covering Oracle Insurance, Guidewire ClaimCenter, Azure workloads, and the endpoint estate. Establish monthly internal scanning and quarterly perimeter scanning schedules. Define and document patch SLAs: Critical 72 hours, High 7 days, Medium 30 days, Low 90 days. | High | F-008 | R-005 | IT Operations Manager | 01 Apr 2025 | 30 Apr 2025 | 10 | Open
CA-026 | 3 | Apr–Jun 2025 | Develop BCP and DRP covering Oracle Insurance and Guidewire ClaimCenter | Develop a Business Continuity Plan covering cybersecurity incident scenarios (ransomware, data breach, system compromise) and a Disaster Recovery Plan with documented recovery procedures for Oracle Insurance and Guidewire ClaimCenter. Define RTOs and RPOs in consultation with business stakeholders. Assign named BCP/DRP owner. | Critical | F-005 | R-015 | IT Operations Manager / Senior Management | 01 Apr 2025 | 30 Jun 2025 | 20 | Open
CA-027 | 3 | Apr–Jun 2025 | Implement offsite / cloud backup capability for critical systems | Establish an offsite or Azure-based backup capability for Oracle Insurance and Guidewire ClaimCenter data. Ensure backups are encrypted, access-controlled, and geographically separated from the Riyadh primary data centre. Define backup retention schedule aligned to RTO/RPO requirements. | Critical | F-005 | R-015, R-016 | IT Operations Manager | 01 May 2025 | 30 Jun 2025 | 10 | Open
CA-028 | 3 | Apr–Jun 2025 | Conduct backup restoration test | Conduct a formal backup restoration test for Oracle Insurance and Guidewire ClaimCenter. Document test results including actual recovery time, data integrity verification, and any gaps identified. Update BCP/DRP with restoration test findings. | High | F-005 | R-016 | IT Operations Manager | 01 Jun 2025 | 30 Jun 2025 | 3 | Open
PHASE 4 — JULY–OCTOBER 2025 — BCP/DR TESTING & SAMA CSF MATURITY VALIDATION
CA-029 | 4 | Jul–Oct 2025 | Conduct full BCP/DR tabletop exercise and validation | Design and execute a full Business Continuity and Disaster Recovery tabletop exercise simulating a major cybersecurity incident resulting in Oracle Insurance system unavailability. Test escalation, communication, recovery procedures, and SAMA notification workflow. Document lessons learned and update BCP/DRP. | Critical | F-005 | R-015 | CISO / IT Operations Manager | 01 Jul 2025 | 31 Aug 2025 | 10 | Open
CA-030 | 4 | Jul–Oct 2025 | SAMA CSF maturity validation assessment — target Level 3.0 verification | Conduct a formal internal assessment against the SAMA Cybersecurity Framework across all four pillars to validate maturity progression toward Level 3.0. Assess each pillar against target state defined in RCA-P3-003. Identify any remaining gaps, update corrective action plan, and prepare regulatory readiness evidence pack. | High | F-001, F-003, F-004, F-005 | R-001 | CISO | 01 Sep 2025 | 31 Oct 2025 | 20 | Open
TOTAL CORRECTIVE ACTIONS: 30 ¦ Critical: 17 ¦ High: 13 ¦ Live: 2

## Gantt Chart
CORRECTIVE ACTION PLAN — GANTT CHART ¦ Al Ameen Insurance Company ¦ Nov 2024 – Oct 2025
Action ID | Action Title | Priority | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025
PHASE 1: CRITICAL GOVERNANCE & LIVE RISKS
CA-001 | Appoint CISO or designate cybersecurity accountable per... | Critical | ■
CA-002 | IMMEDIATE: Disable shared admin account on Oracle Insur... | Critical | ▲
CA-003 | IMMEDIATE: Rotate all Oracle Insurance administrative c... | Critical | ▲
CA-004 | Enable privileged session logging on Oracle Insurance | Critical | ■
CA-005 | Initiate cybersecurity strategy development | Critical | ■ | ■
CA-006 | Conduct emergency review of Najm, Munich Re, and Swiss ... | Critical | ■
CA-007 | Extend audit log retention to 12 months — Azure AD imme... | Critical | ■
CA-008 | Conduct user access audit — Oracle Insurance, Guidewire... | High | ■
PHASE 2: RISK MANAGEMENT, IR, TRAINING & POLICY
CA-009 | Develop cybersecurity risk assessment methodology | Critical |  |  | ■
CA-010 | Conduct organisation-wide cyber risk assessment | Critical |  |  |  | ■
CA-011 | Develop and implement incident response plan | High |  |  | ■ | ■
CA-012 | Conduct incident response tabletop exercise | High |  |  |  |  | ■
CA-013 | Extend audit log retention to 12 months — Oracle Insura... | High |  |  | ■
CA-014 | Implement centralised log management solution | High |  |  |  | ■ | ■
CA-015 | Develop and launch mandatory security awareness trainin... | High |  |  | ■ | ■ | ■
CA-016 | Integrate security awareness into onboarding programme | High |  |  | ■ | ■
CA-017 | Develop cybersecurity policy framework | Critical |  |  | ■ | ■ | ■
CA-018 | Define and enforce SAMA breach notification procedure | High |  |  | ■
CA-019 | Implement MFA on Oracle Insurance Policy Administration | High |  |  |  | ■
CA-020 | Establish semi-annual access review cycle | High |  |  |  |  | ■
PHASE 3: THIRD-PARTY, VULN MGMT & BCP/DR
CA-021 | Develop third-party cybersecurity management policy | Critical | [5 empty] | ■
CA-022 | Renegotiate Najm contract — add cybersecurity clauses | Critical | [5 empty] | ■ | ■ | ■
CA-023 | Renegotiate Munich Re and Swiss Re reinsurance agreemen... | Critical | [5 empty] | ■ | ■ | ■
CA-024 | Conduct security assessments for Najm, Munich Re, and S... | Critical | [6 empty] | ■ | ■
CA-025 | Implement scheduled vulnerability management programme | High | [5 empty] | ■
CA-026 | Develop BCP and DRP covering Oracle Insurance and Guide... | Critical | [5 empty] | ■ | ■ | ■
CA-027 | Implement offsite / cloud backup capability for critica... | Critical | [6 empty] | ■ | ■
CA-028 | Conduct backup restoration test | High | [7 empty] | ■
PHASE 4: BCP/DR TESTING & SAMA CSF VALIDATION
CA-029 | Conduct full BCP/DR tabletop exercise and validation | Critical | [8 empty] | ■ | ■
CA-030 | SAMA CSF maturity validation assessment — target Level ... | High | [10 empty] | ■ | ■
LEGEND: ■ = Planned action window ▲ = Live risk — immediate action required

## Dashboard
CORRECTIVE ACTION PLAN DASHBOARD — Al Ameen Insurance Company ¦ RCA-P3-005 ¦ 31 October 2024
NCA ECC-1:2018 + SAMA CSF Compliance Audit ¦ Remediation Period: November 2024 – October 2025
Total Actions | Critical Priority | High Priority | Live Risk Actions | Phase 1 Actions | Phase 2 Actions | Phase 3+4 Actions
30 | 17 | 13 | 2 | 8 | 12 | 10
Nov 2024 – Oct 2025 | Immediate attention | Within 30 days | Action within 5 days | Nov–Dec 2024 | Jan–Mar 2025 | Apr–Oct 2025
ACTIONS BY PHASE
Phase | Period | Focus | Total Actions | Critical | High | Live
Phase 1 | Nov–Dec 2024 | Critical governance & live risks | 8 | 7 | 1 | 2
Phase 2 | Jan–Mar 2025 | Risk management, IR, training, policy | 12 | 3 | 9 | 0
Phase 3 | Apr–Jun 2025 | Third-party, vuln mgmt, BCP/DR framework | 8 | 6 | 2 | 0
Phase 4 | Jul–Oct 2025 | BCP/DR testing, SAMA CSF validation | 2 | 1 | 1 | 0
⚠ LIVE RISKS — ACTION REQUIRED WITHIN 5 BUSINESS DAYS OF REPORT RECEIPT
Action ID | Action Title | Finding | Risk Ref | Owner | Target | Status
CA-002 | IMMEDIATE: Disable shared admin account on Oracle Insurance — create individual named accounts | F-007 | R-006 | IT Operations Manager | 07 Nov 2024 | Open — LIVE
CA-003 | IMMEDIATE: Rotate all Oracle Insurance administrative credentials | F-007 | R-006 | IT Operations Manager | 14 Nov 2024 | Open — LIVE