RESOLUTE COMPLIANCE ADVISORY LLP Governance · Risk · Compliance

ENGAGEMENT LETTER & SCOPE OF WORK ECC-2:2024 Delta Assessment — Al Ameen Insurance Company

|  | Prepared for Al Ameen Insurance Company Insurance · Riyadh, Kingdom of Saudi Arabia Engagement Period: 03 February 2025 – 30 April 2025 |
| --- | --- |

| Prepared by kay Shahbaaz GRC Auditor | Date 03 February 2025 | Document Ref RCA-P3C-001 |
| --- | --- | --- |

CONFIDENTIALITY NOTICE This document is prepared exclusively for Al Ameen Insurance Company and contains confidential and proprietary information belonging to Resolute Compliance Advisory LLP. It may not be disclosed, reproduced, or distributed to any third party without the prior written consent of Resolute Compliance Advisory LLP. Unauthorised use or disclosure is strictly prohibited.

Document Control

| Field | Details |
| --- | --- |
| Document Title | Engagement Letter & Scope of Work — ECC-2:2024 Delta Assessment |
| Document Ref | RCA-P3C-001 |
| Client | Al Ameen Insurance Company |
| Project | NCA ECC-2:2024 Delta Assessment — Returning Engagement |
| Prepared by | kay Shahbaaz |
| Reviewed by | Resolute Compliance Advisory LLP |
| Date | 03 February 2025 |
| Version | v1.0 |
| Classification | CONFIDENTIAL |
| Status | Final |

| 1 | Introduction |
| --- | --- |

This document constitutes the formal Engagement Letter and Scope of Work between Resolute Compliance Advisory LLP (hereinafter referred to as "the Firm") and Al Ameen Insurance Company (hereinafter referred to as "the Client") for the NCA ECC-2:2024 Delta Assessment engagement.

This engagement is a continuation of Project RCA-P3 (July 2024 – October 2024), in which Resolute Compliance Advisory LLP conducted a full NCA ECC-1:2018 compliance audit and SAMA CSF maturity assessment for Al Ameen Insurance Company. This delta assessment is designed to evaluate the Client's current cybersecurity posture against the updated NCA Essential Cybersecurity Controls version 2:2024 (ECC-2:2024), which supersedes ECC-1:2018 as the applicable regulatory baseline from October 2024.

1.1  Background and Context

Al Ameen Insurance Company is a regulated insurance provider headquartered in Riyadh, Kingdom of Saudi Arabia, with branches in Jeddah and Dammam. The Client operates under the supervision of the Saudi Central Bank (SAMA) and is subject to mandatory compliance with NCA cybersecurity regulations.

The original ECC-1:2018 audit (RCA-P3) identified an overall conformance rate of 29.0% (33 of 114 controls conformant) and a SAMA CSF maturity score of 1.6 out of 4.0. A Corrective Action Plan (CAP) comprising 30 actions across four phases was issued in October 2024, with Phase 1 actions targeting the period November–December 2024.

By February 2025, Phase 1 of the CAP is substantially complete. The Client has appointed an IT Security Manager, revoked shared Oracle Insurance production system credentials, enabled multi-factor authentication on privileged Azure AD accounts, extended log retention to 12 months in compliance with SAMA requirements, delivered an initial all-staff security awareness session, and completed an inventory of critical systems. A top-level cybersecurity policy framework has been drafted and ratified by the Board.

NCA ECC-2:2024, released in October 2024, restructures the control framework from 114 controls across 5 domains to 108 controls, incorporating new requirements relating to cryptographic agility, quantum-readiness, updated cloud security baselines, and stricter supply chain and localised vendor governance requirements. A delta assessment is required to evaluate the Client's posture against these updated requirements and to identify new gaps introduced by the revised framework.

1.2  Engagement Objectives

This engagement has four primary objectives:

| 01 | Assess the Client's remediation progress against the 30 corrective actions issued in the Project 3 CAP (RCA-P3-005), providing documented evidence of control improvements. |
| --- | --- |
| 02 | Conduct a full delta assessment against all 108 NCA ECC-2:2024 controls, identifying new gaps introduced by the updated framework that were not present in ECC-1:2018. |
| 03 | Produce an updated risk register reflecting the current threat and control landscape, including revised risk scores where remediation has been demonstrated. |
| 04 | Deliver an Executive Summary suitable for presentation to Al Ameen's Board and SAMA, demonstrating measurable progress since the October 2024 audit. |

| 2 | Scope of Work |
| --- | --- |

The scope of this delta assessment covers the following:

2.1  ECC-2:2024 Delta Control Assessment

Assessment of the Client's cybersecurity controls against all 108 controls in NCA ECC-2:2024, structured as a delta assessment. The assessment will:

(a)  Evaluate controls that existed under ECC-1:2018 for improvement or regression relative to the October 2024 baseline.

(b)  Evaluate new or restructured controls introduced in ECC-2:2024 that have no direct ECC-1:2018 equivalent.

(c)  Document conformance status for each control as Conformant, Partial, or Non-Conformant with supporting evidence references.

2.2  CAP Remediation Verification

Review and verification of evidence submitted by the Client against each of the 30 corrective actions in the Project 3 CAP. Each action will be assessed as Complete, In Progress, or Not Started, with supporting evidence references documented in the fieldwork checklist.

2.3  System and Process Walkthroughs

The following systems and processes will be included in fieldwork walkthroughs:

| # | Item | Details |
| --- | --- | --- |
| 01 | Oracle Insurance Policy Administration | On-premise, Riyadh DC — access controls, credential management, audit logging |
| 02 | Guidewire ClaimCenter | On-premise, Riyadh DC — access controls, change management, logging |
| 03 | Azure Active Directory (Hybrid) | Privileged access, MFA configuration, conditional access policies |
| 04 | Azure KSA Region Workloads | Cloud security baseline, encryption, monitoring configuration |
| 05 | Microsoft 365 | Data governance settings, email security, DLP policy status |
| 06 | Third-Party Interfaces | Najm (motor claims), Shafafiyah (SAMA reporting) — connection security, contractual security clauses |
| 07 | Cybersecurity Policy Framework | Ratified top-level policy and supporting procedure documentation |
| 08 | Log Management (Azure Monitor / Sentinel) | 12-month retention verification, alert configuration, SIEM coverage |

2.4  Stakeholder Interviews

Interviews will be conducted with the following stakeholders:

| Role | Focus Areas |
| --- | --- |
| IT Security Manager (newly appointed) | Cybersecurity governance, policy ratification, remediation progress overview |
| IT Operations Manager | System walkthroughs, vulnerability management, log management, change control |
| Oracle Insurance System Administrator | Credential management, access controls, audit logging on production system |
| Azure / Cloud Administrator | Azure AD MFA, conditional access, cloud security configuration, Azure Sentinel |
| Procurement / Contracts Representative | Third-party contract review — Najm, Shafafiyah, Munich Re, Swiss Re security clauses |
| Internal Audit Representative (if applicable) | Governance oversight, audit findings follow-up |

| 3 | Out of Scope |
| --- | --- |

The following items are explicitly excluded from this engagement:

1.  Implementation of controls or remediation activities — these remain the sole responsibility of the Client

2.  Penetration testing, technical vulnerability assessments, or red team exercises

3.  Certification audit or formal regulatory submission — this engagement is an advisory assessment only

4.  SAMA CSF maturity re-assessment — SAMA CSF maturity was assessed in Project 3 (RCA-P3); a full re-assessment is not within the scope of this delta engagement; references to SAMA CSF will be limited to contextual commentary where directly relevant to ECC-2:2024 findings

5.  Reinsurance counterparty assessments (Munich Re, Swiss Re) — the assessment will review the Client's management of these relationships but will not conduct assessments of the counterparties themselves

6.  Assessment of NCA ECC-1:2018 controls that are no longer present in ECC-2:2024 — the ECC-2:2024 framework is the sole assessment baseline for this engagement

| 4 | Deliverables |
| --- | --- |

The following deliverables will be produced under this engagement:

| Ref | Document | Format | Due |
| --- | --- | --- | --- |
| RCA-P3C-001 | Delta Assessment Engagement Letter & Scope of Work | Word | 03 February 2025 |
| RCA-P3C-002 | ECC-2:2024 Delta Fieldwork Checklist | Excel | 14 March 2025 |
| RCA-P3C-003 | Delta Assessment Findings Report | Word | 31 March 2025 |
| RCA-P3C-004 | Updated Risk Register | Excel | 15 April 2025 |
| RCA-P3C-005 | Executive Summary | Word | 30 April 2025 |

| 5 | Engagement Timeline |
| --- | --- |

The engagement will be executed across four phases within the period 03 February 2025 to 30 April 2025:

| Phase | Period | Activity |
| --- | --- | --- |
| Phase 1 — Mobilisation | 03 – 07 Feb 2025 | Engagement kick-off; document request list issued; stakeholder interviews scheduled; baseline comparison of Project 3 findings initialised |
| Phase 2 — Fieldwork | 10 Feb – 14 Mar 2025 | ECC-2:2024 delta control assessment; review of remediation evidence against Project 3 CAP; system walkthroughs (Oracle Insurance, Guidewire, Azure AD); stakeholder interviews |
| Phase 3 — Analysis & Reporting | 17 – 31 Mar 2025 | Delta gap analysis; updated risk scoring; draft findings report issued to client for review |
| Phase 4 — Finalisation | 01 – 30 Apr 2025 | Client review period; findings validated; updated Risk Register and Executive Summary issued; engagement closed |

Note: As a returning client engagement, the mobilisation phase is abbreviated. Document request lists and interview scheduling will be issued on 03 February 2025. Fieldwork is expected to commence the week of 10 February 2025, subject to Client availability.

| 6 | Roles and Responsibilities |
| --- | --- |

| Resolute Compliance Advisory LLP | Al Ameen Insurance Company |
| --- | --- |
| Conduct ECC-2:2024 delta control assessment against all 108 controls | Provide access to systems, documentation, and personnel as required |
| Review and validate remediation evidence submitted against Project 3 corrective action plan | Designate a primary point of contact to coordinate fieldwork activities |
| Conduct stakeholder interviews and system walkthroughs | Ensure availability of IT Operations Manager and relevant system owners during fieldwork |
| Produce all five deliverables listed in Section 4 within agreed timelines | Review draft findings report and provide written responses within 10 business days |
| Maintain confidentiality of all client information in accordance with the Non-Disclosure Agreement in force from Project 3 | Implement corrective actions — remediation remains the sole responsibility of the Client |

| 7 | Fees and Payment Terms |
| --- | --- |

| Item | Detail |
| --- | --- |
| Engagement Type | Returning client — delta assessment (reduced scope vs initial engagement) |
| Fixed Fee | SAR 48,000 (inclusive of all professional fees) |
| Expenses | Travel and accommodation, if required, billed at cost with prior written approval |
| Payment Schedule | 50% upon engagement commencement (03 February 2025); 50% upon delivery of final Executive Summary (30 April 2025) |
| Currency | Saudi Riyal (SAR) |
| Invoicing | Invoices issued to Al Ameen Insurance Company — Accounts Payable department |

| 8 | General Terms and Conditions |
| --- | --- |

8.1  Confidentiality

All information exchanged under this engagement is subject to the Non-Disclosure Agreement (NDA) executed between the parties during the Project 3 engagement (RCA-P3). The NDA remains in full force and effect for the duration of this engagement and for a period of three years following its conclusion.

8.2  Independence

Resolute Compliance Advisory LLP confirms that this engagement is conducted as an independent advisory assessment. The Firm has no commercial interest in any system, product, or vendor referenced in the assessment findings. All findings and recommendations are based solely on the evidence reviewed during fieldwork.

8.3  Reliance on Client Information

The findings of this assessment are based on information, documentation, and system access provided by the Client. Resolute Compliance Advisory LLP accepts no liability for findings that arise from incomplete, inaccurate, or withheld information. The Client is responsible for ensuring that all relevant documentation and personnel are made available during the fieldwork period.

8.4  Limitation of Liability

The total liability of Resolute Compliance Advisory LLP under this engagement shall not exceed the total professional fees paid by the Client for this engagement. The Firm shall not be liable for indirect, consequential, or incidental losses arising from the use of, or reliance upon, the deliverables produced under this engagement.

8.5  Governing Law

This engagement letter is governed by the laws of the Kingdom of Saudi Arabia. Any disputes arising under this engagement shall be subject to the exclusive jurisdiction of the competent courts of Riyadh.

8.6  Amendments

Any amendments to the scope of work, timeline, or fees must be agreed in writing by both parties prior to implementation. Verbal agreements or email exchanges do not constitute amendments to this engagement letter unless confirmed in a formal written addendum signed by authorised representatives of both parties.

| 9 | Acceptance |
| --- | --- |

By signing below, both parties confirm their agreement to the terms, scope, deliverables, and conditions set out in this Engagement Letter.

| For and on behalf of RESOLUTE COMPLIANCE ADVISORY LLP _________________________________ kay Shahbaaz GRC Auditor Date: 03 February 2025 |  | For and on behalf of AL AMEEN INSURANCE COMPANY _________________________________ Name: ___________________________ Title: ____________________________ Date: ____________________________ |
| --- | --- | --- |

This document is issued under the authority of Resolute Compliance Advisory LLP. Queries regarding this engagement should be directed to kay Shahbaaz, GRC Auditor, Resolute Compliance Advisory LLP.