## Cover
RESOLUTE COMPLIANCE ADVISORY LLP
Governance · Risk · Compliance
INFORMATION SECURITY RISK REGISTER
ISO 27001:2022 / GDPR / DPDP Act 2023 · Medlink India Pvt. Ltd.
Document Ref | RCA-P2-006
Client | Medlink India Pvt. Ltd.
Prepared by | kay Shahbaaz, GRC Analyst
Assessment Date | 25 March – 30 April 2024
Report Date | 31 May 2024
Version | v1.0
Classification | CONFIDENTIAL
Methodology | Likelihood × Impact (1–5 scale); Score = L × I
Rating Bands | Critical: 20–25 ¦ High: 12–19 ¦ Medium: 6–11 ¦ Low: 1–5
Total Risks | 31 risks across 11 domains
RISK RATING LEGEND
Critical (20–25) | Immediate escalation required. Live risk or fundamental control failure.
High (12–19) | Significant risk requiring structured remediation within 90 days.
Medium (6–11) | Moderate risk — address within programme timeline.
Low (1–5) | Low risk — monitor and review annually.
RISK TREATMENT OPTIONS
Treat | Implement controls to reduce likelihood and/or impact to an acceptable residual level.
Transfer | Transfer the risk to a third party (e.g. insurance, contractual liability) — risk owner retains accountability.
Accept | Accept the risk — residual risk is within the organisation's risk appetite. Document formally.
Terminate | Cease the activity giving rise to the risk. Not used in this register — all risks relate to core operations.

## Dashboard
RISK REGISTER DASHBOARD · Medlink India Pvt. Ltd. · RCA-P2-006 · CONFIDENTIAL
RISK COUNT BY RATING
| Critical | High | Medium | Low | TOTAL
| 6 | 17 | 8 | 0 | 31
⚠ LIVE RISKS: 2 — R-004 (AWS IAM credentials) and R-005 (Twilio token) require IMMEDIATE action
RISK DISTRIBUTION BY DOMAIN
| Domain | Risk Count | Critical | High | Med/Low
| Access Control & Identity | 3 | — | 2 | 1
| Application & Development Security | 3 | — | 2 | 1
| Business Continuity | 1 | — | — | 1
| Data Protection — Encryption | 3 | 1 | 1 | 1
| Governance & Policy | 3 | 2 | 1 | —
| Incident Response & Breach Notification | 3 | 1 | 2 | —
| Personnel Security | 2 | — | 2 | —
| Physical Security | 2 | — | — | 2
| Privacy & Consent | 3 | 1 | 2 | —
| Regulatory & Emerging | 1 | — | 1 | —
| Secrets & Credentials | 3 | 1 | 2 | —
| Third-Party & Supply Chain | 3 | — | 1 | 2
| Vendor Management | 1 | — | 1 | —
| TOTAL | 31 | 6 | 17 | 8

## Risk Register
INFORMATION SECURITY RISK REGISTER · Medlink India Pvt. Ltd. · RCA-P2-006 · CONFIDENTIAL · 31 May 2024
Risk ID | Domain | Asset / Process | Threat | Vulnerability | Likelihood (1–5) | Impact (1–5) | Inherent Score | Inherent Rating | Treatment | Controls / Actions | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Owner | Finding Ref | Live Risk? | Notes
R-001 | Governance & Policy | Information Security Programme | Absence of governance direction leading to uncoordinated security decision-making | No approved IS policy; no formal ISMS established; no board-level security mandate | 4 | 4 | 16 | High | Treat | Approve IS policy; appoint ISMS owner; define IS roles and responsibilities | 2 | 3 | 6 | Medium | CTO / Board | F-001 | —
R-002 | Governance & Policy | Regulatory Compliance — UK GDPR | ICO enforcement action for non-compliance with UK GDPR processor obligations | No Article 28 DPAs; no DPIA conducted; no DPO appointed | 5 | 5 | 25 | Critical | Treat | Execute DPAs with UK clients; conduct DPIA; appoint DPO (G-001, G-002, G-003) | 2 | 4 | 8 | Medium | Legal / CTO | G-001 / G-002 / G-003 | — | ICO fines up to GBP 8.75m or 2% global turnover
R-003 | Governance & Policy | Regulatory Compliance — DPDP Act 2023 | Data Protection Board enforcement action for non-compliant consent and rights gaps | Non-compliant consent mechanism; no rights mechanism; no Grievance Officer | 5 | 4 | 20 | Critical | Treat | Redesign consent flow; implement rights mechanism; appoint Grievance Officer (D-001, D-003, D-004) | 2 | 3 | 6 | Medium | Legal / Engineering | D-001 / D-003 / D-004 | — | Penalty up to INR 250 crore under DPDP Act Schedule
R-004 | Secrets & Credentials | AWS Production Environment | Unauthorised access to AWS production environment using exposed IAM credentials | AWS IAM access key hardcoded in private GitHub repository; no secrets scanning in CI/CD | 4 | 5 | 20 | Critical | Treat | IMMEDIATE: rotate IAM key; implement AWS Secrets Manager; enable GitHub secret scanning | 1 | 5 | 5 | Low | Head of Engineering | F-002 | LIVE RISK | Credentials confirmed active at assessment date. CloudTrail review required for past 90 days.
R-005 | Secrets & Credentials | Patient Communications — Twilio SMS | Unauthorised use of Twilio API token to send fraudulent SMS to patients | Twilio API token hardcoded in private GitHub repository; no token rotation policy | 4 | 4 | 16 | High | Treat | IMMEDIATE: regenerate Twilio token; store in AWS Secrets Manager; enforce rotation policy | 1 | 3 | 3 | Low | Head of Engineering | F-002 | LIVE RISK | Token active at assessment date. Fraudulent SMS to patients (e.g. phishing links) is a realistic attack scenario.
R-006 | Secrets & Credentials | Developer Credentials — General | Future credential leakage through hardcoded secrets in new code repositories | No secrets scanning in CI/CD pipeline; no secure coding standards; no developer training | 4 | 4 | 16 | High | Treat | Implement secrets scanning gate in GitHub Actions CI/CD; publish secure coding standards; developer training | 2 | 3 | 6 | Medium | Head of Engineering | F-002 / A.8.28 / A.8.29 | — | Risk of recurrence without systemic controls. F-002 is a symptom; this risk addresses the root cause.
R-007 | Data Protection — Encryption | Patient Diagnostic Data — S3 | Unauthorised access to unencrypted patient diagnostic attachments in S3 | 14 of 31 S3 buckets lack SSE-KMS enforcement; 7 confirmed to contain diagnostic PHI | 4 | 5 | 20 | Critical | Treat | Enforce SSE-KMS via S3 bucket policy on all 31 buckets; S3 Batch Operations retroactive encryption | 1 | 5 | 5 | Low | IT Operations / AWS Admin | F-004 | — | Diagnostic attachments include pathology reports, radiology images — highest sensitivity PHI.
R-008 | Data Protection — Encryption | AWS KMS Key Material | Cryptographic compromise of patient data through long-lived unrotated KMS keys | Three CMKs not rotated since 2019; no key management policy; automatic rotation disabled | 2 | 5 | 10 | Medium | Treat | Enable automatic annual key rotation on all CMKs; document key management policy (F-011) | 1 | 4 | 4 | Low | IT Operations | F-011 | — | Residual risk after rotation remains low — AWS KMS key isolation is strong. Rotation is procedural hygiene.
R-009 | Data Protection — Encryption | PHI in Test Environments | Unauthorised access to production patient data copied into non-production environments | Production PHI used in test/staging environments; no data masking; test env controls weaker | 3 | 5 | 15 | High | Treat | Implement data masking or synthetic data generation for test environments; prohibit PHI in non-prod | 2 | 3 | 6 | Medium | Head of Engineering | A.8.33 | — | Test environment has lower access controls and monitoring than production. PHI in test = uncontrolled exposure.
R-010 | Access Control & Identity | EMR Application — Privileged User Access | Insider threat — authorised user accessing patient records beyond their clinical need | No application-level audit logging; no access recertification; background screening gaps (F-009) | 3 | 5 | 15 | High | Treat | Implement application audit logging (F-012); conduct access recertification; complete background screening (F-009) | 2 | 4 | 8 | Medium | CTO / IT Operations | F-009 / F-012 | — | Healthcare insider threat is high-frequency globally. Absence of audit trail eliminates detection capability.
R-011 | Access Control & Identity | Staff Accounts — Former Employees | Residual access by departed staff due to incomplete offboarding | No formally documented or timed offboarding process; deactivation timing not recorded | 2 | 5 | 10 | Medium | Treat | Document offboarding SLA (same-day deactivation); record deactivation timestamps in HR system | 1 | 4 | 4 | Low | IT Operations / HR | — | — | Azure AD accounts deactivated on departure (confirmed) but timing not formally enforced or recorded.
R-012 | Access Control & Identity | Lab Integration API Access | Unauthorised access to Medlink platform via compromised lab partner API credentials | No security assessment of lab partners; no formal API credential management for integrations | 3 | 4 | 12 | High | Treat | Conduct vendor security assessments (F-005); implement API key rotation and scope restriction for lab integrations | 2 | 3 | 6 | Medium | Head of Engineering / Procurement | F-005 | — | Seven lab partners with persistent API access to the Medlink platform. One compromised partner = patient data at risk.
R-013 | Third-Party & Supply Chain | Lab Integration Partners — PHI Transmission | Patient health data breach at a lab partner system exposing data in transit or at rest | No security assessment, DPA, or contractual security obligations for any of 7 lab partners | 3 | 5 | 15 | High | Treat | Execute DPAs and security questionnaires with all lab partners; require annual VAPT attestation (F-005) | 2 | 4 | 8 | Medium | Legal / CTO | F-005 | — | HL7/FHIR transmissions contain full diagnostic results. Lab partner breach = Medlink patient data breach.
R-014 | Third-Party & Supply Chain | Razorpay — Patient Billing Data | Patient billing data breach at Razorpay payment gateway | No independent security assessment of Razorpay; PCI-DSS compliance vendor-claimed only | 2 | 4 | 8 | Medium | Transfer | Obtain Razorpay PCI-DSS certificate and GDPR/DPDP DPA; contractual security obligations | 1 | 4 | 4 | Low | Finance / Legal | F-005 | — | Razorpay processes payment data only — Medlink does not store card data. Risk partially transferred to Razorpay under PCI-DSS.
R-015 | Third-Party & Supply Chain | AWS — Cloud Infrastructure | AWS service failure or security incident affecting Medlink platform availability or data security | Shared responsibility model; Medlink controls above OS layer; AWS controls infrastructure | 2 | 5 | 10 | Medium | Transfer | AWS shared responsibility acknowledged; Medlink controls enforced (WAF, CloudTrail, IAM, KMS) | 1 | 4 | 4 | Low | IT Operations | — | — | Risk substantially transferred to AWS via contractual SLAs and shared responsibility model. Residual Medlink-layer controls in place.
R-016 | Incident Response & Breach Notification | Patient Data Breach — UK Patients | ICO enforcement for failure to notify a UK patient data breach within 72 hours | No incident response procedure; no breach classification criteria; no ICO notification template | 4 | 5 | 20 | Critical | Treat | Develop IR procedure with 72-hour ICO notification track; appoint IR Lead; tabletop exercise (F-006, G-001) | 2 | 4 | 8 | Medium | CTO / Legal | F-006 | — | GDPR Article 33: 72-hour notification from point of becoming aware. No current capability to meet this.
R-017 | Incident Response & Breach Notification | Patient Data Breach — Indian Patients | DPB enforcement for failure to notify a breach of Indian patient data | No breach notification procedure for DPDP Act Section 8(6) obligations | 4 | 4 | 16 | High | Treat | Develop IR procedure with DPB notification track; implement privacy breach classification (F-006, D-002) | 2 | 3 | 6 | Medium | CTO / Legal | F-006 / D-002 | — | DPDP Act Section 8(6) notification obligation live from commencement. Rules pending — monitor for timeline prescription.
R-018 | Incident Response & Breach Notification | Patient Data Breach — Dual Jurisdiction | Simultaneous UK and Indian patient data breach triggering parallel regulatory investigations | Single breach could affect both AWS London (UK) and AWS Mumbai (India) data; no dual-track IR procedure | 3 | 5 | 15 | High | Treat | Design IR procedure with jurisdiction determination step; parallel notification tracks for ICO and DPB | 2 | 4 | 8 | Medium | CTO / Legal | F-006 | — | Dual-jurisdiction breach is realistic — Medlink's platform spans both AWS regions. Penalty exposure compounds.
R-019 | Privacy & Consent | Patient Consent — Indian Patients | Processing of Indian patient data without lawful consent — DPDP Act Section 6 violation | Single click-through consent; no purpose-specific consent notice; no withdrawal mechanism | 5 | 4 | 20 | Critical | Treat | Redesign consent mechanism; implement granular purpose consent; build withdrawal capability (D-001) | 2 | 3 | 6 | Medium | Engineering / Legal | D-001 | — | Every Indian patient onboarded since August 2023 registered without DPDP-compliant consent. Ongoing live non-compliance.
R-020 | Privacy & Consent | Data Principal Rights — Unresolved Requests | Regulatory complaint from Data Principal for failure to fulfil erasure/access request | No rights mechanism; January 2024 erasure request unresolved; no Grievance Officer | 4 | 3 | 12 | High | Treat | Implement rights request mechanism; resolve outstanding request; appoint Grievance Officer (D-003, D-004) | 2 | 2 | 4 | Low | Legal / CTO | D-003 / D-004 | — | Unresolved erasure request from January 2024 is an existing compliance failure. DPB complaint risk is live.
R-021 | Privacy & Consent | Patient Data Retention — Terminated Clients | Regulatory action for retaining patient data beyond lawful basis following client termination | Two former clients' patient data confirmed retained; no retention schedule; no deletion controls | 4 | 4 | 16 | High | Treat | Assess legal basis for retained data; implement retention schedule and deletion controls (G-004) | 2 | 3 | 6 | Medium | Legal / Engineering | G-004 | — | Former client data retained without lawful basis = processing of special category data in violation of GDPR Article 9.
R-022 | Physical Security | On-Premise Server Room — Backup Tapes | Unauthorised physical access to backup tapes containing copies of patient health data | No CCTV in server room; no visitor log; backup tape encryption status unconfirmed | 2 | 4 | 8 | Medium | Treat | Install server room CCTV; implement visitor log; confirm/implement backup tape encryption (F-008) | 1 | 3 | 3 | Low | IT Operations / Facilities | F-008 | — | Physical breach of backup tapes could yield unencrypted PHI. Server room badge-controlled but unmonitored.
R-023 | Physical Security | Visitor Access — Mumbai Office | Unauthorised visitor access to office areas with potential access to unlocked workstations | No visitor log; visitors escorted but entry/exit not recorded | 2 | 3 | 6 | Medium | Treat | Implement visitor log at reception; brief reception staff; visitor badges | 1 | 2 | 2 | Low | Facilities / Operations | F-008 | — | Low likelihood given escort requirement but absence of log means no audit trail.
R-024 | Application & Development Security | Mobile Application — Patient PHI Interception | Man-in-the-middle attack intercepting patient health data transmitted via mobile app | No certificate pinning on Android and iOS apps; vulnerability identified January 2024 VAPT but not remediated | 2 | 4 | 8 | Medium | Treat | Implement certificate pinning in both mobile apps; establish VAPT finding remediation tracking (F-013) | 1 | 3 | 3 | Low | Head of Engineering | F-013 | — | Attack requires untrusted network positioning. Patient access to health records on public Wi-Fi is realistic.
R-025 | Application & Development Security | Application Audit Trail — Patient Record Access | Inability to detect or investigate unauthorised access to patient records | No application-level audit logging; RDS query logging disabled; no SIEM | 3 | 4 | 12 | High | Treat | Implement application audit logging; enable RDS query logging; centralised log aggregation (F-012) | 2 | 3 | 6 | Medium | Head of Engineering | F-012 | — | Without audit logging, insider threats and external breaches cannot be detected or investigated post-incident.
R-026 | Application & Development Security | CI/CD Pipeline — Code Deployment | Deployment of malicious or vulnerable code to production without security review | No security gate in CI/CD pipeline; no SAST/DAST; no mandatory security sign-off for deployments | 3 | 4 | 12 | High | Treat | Implement secrets scanning and SAST in GitHub Actions pipeline; define security acceptance criteria for releases | 2 | 3 | 6 | Medium | Head of Engineering | A.8.29 | — | F-002 credentials were committed to code with no automated detection. Pipeline security gate would have caught this.
R-027 | Personnel Security | Engineering Team — Unscreened Staff with PHI Access | Insider threat from unscreened engineers with privileged access to patient health systems | 34 of 60 directly hired engineers have no background check on file | 3 | 5 | 15 | High | Treat | Implement mandatory background screening for all PHI-access roles; retrospective programme for existing staff (F-009) | 2 | 4 | 8 | Medium | HR / CTO | F-009 | — | 57% of engineering team has access to PHI systems without background verification. Insider risk cannot be assessed.
R-028 | Personnel Security | Security Awareness — Phishing and Social Engineering | Successful phishing or social engineering attack leading to credential compromise or data breach | No annual security awareness training; no phishing simulation; training last reviewed 2022 | 4 | 4 | 16 | High | Treat | Implement annual security awareness training; quarterly phishing simulations; developer secure coding training (F-007) | 2 | 3 | 6 | Medium | CTO / HR | F-007 | — | Phishing is the primary initial access vector in healthcare sector breaches. Last training 2022 predates DPDP Act entirely.
R-029 | Business Continuity | Platform Availability — Healthcare Client Dependency | Extended platform outage causing disruption to clinical operations at hospital clients | No formal BCM plan; recovery objectives not documented; backup restoration not tested since Q3 2023 | 2 | 5 | 10 | Medium | Treat | Document ICT continuity plan; define RTO/RPO; schedule annual backup restoration test | 1 | 4 | 4 | Low | CTO / IT Operations | — | — | Medlink's clients are healthcare providers — platform unavailability directly impacts patient care delivery.
R-030 | Vendor Management | Vendor Security Programme — Systemic Gap | Security incidents at multiple unassessed third-party vendors causing cascading data breaches | No vendor security assessment framework; no annual review of any vendor; no contractual security obligations | 3 | 5 | 15 | High | Treat | Develop vendor security assessment framework; prioritise lab partners, Razorpay, Twilio; annual review cycle (F-005) | 2 | 3 | 6 | Medium | CTO / Procurement | F-005 | — | Seven lab partners, Razorpay, Twilio, and AWS SES all process Medlink patient data with no security governance.
R-031 | Regulatory & Emerging | DPDP Act Implementing Rules — Compliance Gap | Exposure to non-compliance with DPDP Act obligations prescribed in implementing rules upon notification | DPDP Act rules pending; breach notification timelines, DPB procedures, and retention periods not yet specified | 3 | 4 | 12 | High | Treat | Monitor MeitY rules notification; pre-position procedures and controls to flex upon notification (D-002) | 2 | 3 | 6 | Medium | Legal / Compliance | D-002 | — | Rules could specify shorter notification timelines or additional obligations. Current gap is structural — pre-positioning is the only mitigation.

## Risk Heatmap
RISK HEATMAP — Likelihood vs Impact · Medlink India Pvt. Ltd. · RCA-P2-006
IMPACT →
| 1 — Negligible | 2 — Minor | 3 — Moderate | 4 — Significant | 5 — Severe
5 — Almost Certain |  |  |  | R-003 R-019 | R-002
4 — Likely |  |  | R-020 | R-001 R-005 R-006 R-017 R-021 R-028 | R-004 R-007 R-016
3 — Possible |  |  |  | R-012 R-025 R-026 R-031 | R-009 R-010 R-013 R-018 R-027 R-030
2 — Unlikely |  |  | R-023 | R-014 R-022 R-024 | R-008 R-011 R-015 R-029
1 — Rare
HEATMAP COLOUR KEY
Critical (20–25)
High (12–19)
Medium (6–11)
Low (1–5)
Note: Heatmap plots INHERENT risk scores (pre-treatment). Residual risk scores are documented in the Risk Register sheet.