## Dashboard
RESOLUTE COMPLIANCE ADVISORY LLP ¦ RISK REGISTER
RCA-P4-005 · Rawabi Health Services Co. · NCA ECC-1:2018 + PDPL Compliance Audit · CONFIDENTIAL
Client |  | Rawabi Health Services Co.
Audit Period |  | 10 November 2024 – 31 January 2025
Frameworks |  | NCA ECC-1:2018 ¦ Saudi PDPL
Lead Auditor |  | kay Shahbaaz ¦ GRC Auditor
Methodology |  | Likelihood × Impact (1–5 scale) ¦ Score 1–25
Document Ref |  | RCA-P4-005 ¦ v1.0 ¦ CONFIDENTIAL
Risk Summary by Rating
Rating | Count | % of Total | Band | Description
CRITICAL | 5 | 20% | Score 20–25
HIGH | 8 | 32% | Score 12–19
MEDIUM | 9 | 36% | Score 6–11
LOW | 3 | 12% | Score 1–5
TOTAL | 25 | 100% | —
Risk Scoring Matrix (Likelihood × Impact)
Likelihood \ Impact → | 1 | 2 | 3 | 4 | 5
L5 | 5 | 10 | 15 | 20 | 25
L4 | 4 | 8 | 12 | 16 | 20
L3 | 3 | 6 | 9 | 12 | 15
L2 | 2 | 4 | 6 | 8 | 10
L1 | 1 | 2 | 3 | 4 | 5

## Risk_Register
Risk Register ¦ Rawabi Health Services Co. ¦ NCA ECC-1:2018 + PDPL Compliance Audit ¦ RCA-P4-005
Audit Period: 10 November 2024 – 31 January 2025 · Methodology: Likelihood × Impact (1–5) · Lead Auditor: kay Shahbaaz · CONFIDENTIAL
Risk ID | Domain | Risk Description | Root Cause / Trigger | L (1-5) | I (1-5) | Score | Rating | Current Controls | Risk Owner (Client) | Treatment | Finding Ref | Status
GOVERNANCE & STRATEGY
R-001 | Governance & Strategy | Absence of cybersecurity strategy leads to uncoordinated control investment and unmanaged aggregate risk exposure | No cybersecurity strategy or governance framework in place; no CISO or designated cybersecurity lead; ad hoc security decisions | 4 | 4 | 16 | HIGH | No current controls — security decisions made reactively with no governance framework | COO / IT Manager | Treat — develop and approve cybersecurity strategy and governance framework | F-001 | Open
R-002 | Governance & Strategy | Non-compliance with NCA ECC-1:2018 exposes organisation to NCA regulatory enforcement action | Current ECC conformance of 36% with multiple Critical and High control gaps across all domains | 3 | 4 | 12 | HIGH | No current controls — no compliance programme or monitoring in place | COO | Treat — initiate formal ECC compliance remediation programme | F-001 | Open
R-003 | Governance & Strategy | Absence of cybersecurity budget and investment planning results in continued control gaps | No dedicated cybersecurity budget line; no business case process for security investment | 3 | 3 | 9 | MEDIUM | No current controls | COO / Finance | Treat — establish cybersecurity budget as part of strategy development | F-001 | Open
ACCESS CONTROL & IDENTITY
R-004 | Access Control & Identity | Absence of MFA on Active Directory and Microsoft 365 enables credential compromise and account takeover | MFA not enforced organisation-wide; on-premise AD with no conditional access policies; Microsoft 365 admin accounts without MFA | 4 | 4 | 16 | HIGH | Antivirus deployed on endpoints; password policy partially enforced in AD | IT Manager | Treat — enable MFA for all privileged and remote access accounts; configure Microsoft 365 Conditional Access | — | Open
R-005 | Access Control & Identity | Stale or orphaned Active Directory accounts provide persistent unauthorised access pathways | No formal joiner/mover/leaver process; account lifecycle not managed; no periodic access review conducted | 3 | 4 | 12 | HIGH | No current controls — no access review or account cleanup process | IT Manager | Treat — implement account lifecycle management; conduct immediate AD account audit | — | Open
R-006 | Access Control & Identity | Excessive privileged access on Napas HIS and SAP Business One increases insider threat and compromise impact | Privileged access not formally managed; no least-privilege model; admin credentials shared informally | 3 | 4 | 12 | HIGH | Basic AD group structure in place but not enforced with least-privilege | IT Manager | Treat — implement privileged access management; restrict admin accounts to named individuals | — | Open
R-007 | Access Control & Identity | Weak or reused passwords across clinical systems enable brute-force or credential-stuffing attacks | Password policy not consistently enforced across Napas HIS and clinical workstations; no complexity validation on all systems | 3 | 3 | 9 | MEDIUM | AD password policy exists but not applied to all systems | IT Manager | Treat — enforce consistent password policy across all systems; integrate Napas HIS with AD authentication | — | Open
NETWORK SECURITY
R-008 | Network Security | Flat network architecture enables unrestricted lateral movement between clinical and administrative systems | No VLAN segmentation; no internal firewall rules; Napas HIS, Agfa PACS, SAP B1, and user endpoints on the same broadcast domain | 5 | 5 | 25 | CRITICAL | Perimeter firewall provides internet boundary protection only | IT Manager | Treat — design and implement network segmentation with clinical, imaging, admin, and management zones | F-004 | Open
R-009 | Network Security | Ransomware propagation across flat network could encrypt all clinical systems simultaneously, halting patient care | Flat network (R-008) combined with no EDR, no vulnerability management, and no incident response capability | 4 | 5 | 20 | CRITICAL | Antivirus deployed but definitions outdated on 23% of endpoints; no EDR | IT Manager | Treat — network segmentation (F-004); EDR deployment; incident response plan | F-004, F-007 | Open
R-010 | Network Security | Unmonitored wireless network access provides potential entry point into clinical network | Wireless network not confirmed as segmented from clinical systems; no guest network isolation verified | 2 | 3 | 6 | MEDIUM | WPA2 in use — confirmed during walkthrough | IT Manager | Treat — confirm wireless segmentation; implement guest network isolation | — | Open
THIRD-PARTY & VENDOR
R-011 | Third-Party & Vendor | Uncontrolled Napas vendor remote access to live HIS — LIVE RISK — enables immediate unauthorised access to all patient health records | Shared admin credential not rotated in 18+ months; no VPN or jump server; no session logging; no security clauses in Napas contract | 5 | 5 | 25 | CRITICAL | No mitigating controls — direct internet access with shared credentials and no monitoring | IT Manager | Treat — IMMEDIATE: rotate credentials; implement VPN/jump server; enable session logging; issue data protection addendum | F-003 | LIVE RISK — Immediate
R-012 | Third-Party & Vendor | No DPA with Bupa Arabia — patient health data shared without contractual data protection framework | Insurance eligibility data sharing with Bupa Arabia operates under commercial contract with no data protection clauses | 4 | 4 | 16 | HIGH | No current controls — no DPA, no security obligations on Bupa Arabia | COO / Legal | Treat — execute PDPL-compliant DPA with Bupa Arabia | P-002 | Open
R-013 | Third-Party & Vendor | No DPA with Nphies — clinical records submitted to national health platform without data governance framework | Nphies submission operates under MoH mandate with no documented data governance agreement from Rawabi's side | 4 | 3 | 12 | HIGH | MoH mandate provides legal basis for submission but no DPA documents obligations | COO / Legal | Treat — obtain and execute Nphies data governance framework | P-002 | Open
R-014 | Third-Party & Vendor | Al Bilad Lab external reference laboratory shares patient specimen and result data without data processing agreement | Laboratory referral arrangement in place; no data protection addendum; no defined data handling or disposal obligations on Al Bilad Lab | 3 | 3 | 9 | MEDIUM | No current controls | IT Manager / Legal | Treat — execute data processing addendum with Al Bilad Lab | P-002 | Open
ENDPOINT & INFRASTRUCTURE
R-015 | Endpoint & Infrastructure | Unpatched Windows endpoints (41 of 180 on 2021 builds) expose organisation to known critical CVEs | No patch management policy or schedule; reactive patching only; vulnerability scanning absent | 4 | 4 | 16 | HIGH | Antivirus deployed; definitions outdated on 23% of endpoints | IT Manager | Treat — implement patch management policy; conduct immediate baseline patching of oldest endpoints | F-007 | Open
R-016 | Endpoint & Infrastructure | Absence of EDR leaves endpoints without behavioural detection capability against advanced threats | Only antivirus deployed; no EDR solution in place; no endpoint telemetry or alert management | 3 | 4 | 12 | HIGH | Antivirus provides signature-based detection only | IT Manager | Treat — evaluate and deploy EDR solution across all 180 endpoints | F-007 | Open
R-017 | Endpoint & Infrastructure | Napas HIS server running unvalidated patch level risks exploitation of server-side vulnerabilities | Napas HIS server OS (Windows Server 2016) patch level unconfirmed; no patch record available; vendor-managed updates not verified | 3 | 5 | 15 | HIGH | Napas vendor provides support but no patch validation record available | IT Manager | Treat — confirm Napas HIS server patch level with vendor; establish patch validation process for HIS | F-007 | Open
DATA PROTECTION & PRIVACY
R-018 | Data Protection & Privacy | Processing patient health data without documented lawful basis or consent exposes organisation to SDAIA enforcement action | No PDPL compliance programme; no consent form; no lawful basis assessment conducted; 1,800 patient visits per month generating sensitive data | 5 | 5 | 25 | CRITICAL | No current controls — ongoing daily PDPL violation across all patient interactions | COO / Legal | Treat — IMMEDIATE: design PDPL-compliant consent form; assess lawful basis for all processing activities | P-001 | Open
R-019 | Data Protection & Privacy | Absence of breach notification procedure means 72-hour SDAIA notification obligation cannot be met in event of breach | No IR plan; no breach definition; no SDAIA contact information; no breach assessment process | 4 | 4 | 16 | HIGH | No current controls | IT Manager / COO | Treat — develop breach notification procedure as part of IR plan | P-003 | Open
R-020 | Data Protection & Privacy | Non-compliant privacy notice and absence of data subject rights mechanism exposes organisation to patient complaints and SDAIA investigation | No privacy notice published; no data subject rights procedure; patients not informed of their PDPL rights | 3 | 3 | 9 | MEDIUM | No current controls | COO / Operations | Treat — publish PDPL-compliant privacy notice; implement data subject rights mechanism | P-004, P-005 | Open
R-021 | Data Protection & Privacy | Health data transmitted between clinical systems and Microsoft 365 (Teams/SharePoint) without defined governance increases exfiltration and misuse risk | Home healthcare team uses Teams to share patient care plans; no data classification applied to M365; no DLP controls | 3 | 4 | 12 | HIGH | Microsoft 365 built-in security features available but not configured | IT Manager | Treat — implement M365 data classification and DLP policies; restrict health data in Teams to approved channels | — | Open
INCIDENT RESPONSE
R-022 | Incident Response | Absence of incident response plan means cybersecurity incidents will be managed reactively with no containment capability | No IR policy, procedure, or team defined; two prior incidents in 2024 managed ad hoc with no documentation | 4 | 5 | 20 | CRITICAL | No current controls | IT Manager | Treat — develop and approve incident response plan; designate IR team; conduct tabletop exercise | F-005 | Open
R-023 | Incident Response | Prior IT incidents not assessed for PDPL data breach implications — unidentified notification obligations may exist | Ransomware attempt (March 2024) and HIS outage (July 2024) not assessed for patient data exposure | 3 | 4 | 12 | HIGH | No current controls — no retrospective assessment conducted | IT Manager / Legal | Treat — retrospectively assess both incidents for PDPL breach implications; document assessment outcomes | F-005, P-003 | Open
PHYSICAL SECURITY
R-024 | Physical Security | Medina branch clinic operates without confirmed IT security controls equivalent to Jeddah HQ | Physical walkthrough conducted at Jeddah only; Medina site IT security posture not independently verified; remote IT support arrangements unclear | 2 | 3 | 6 | MEDIUM | Jeddah DC controls confirmed; Medina not assessed in person | IT Manager | Treat — conduct remote or on-site IT security review of Medina branch; document security posture | — | Open
BUSINESS CONTINUITY
R-025 | Business Continuity | No tested backup integrity or offsite recovery — ransomware or disaster event could result in permanent loss of all patient health records | On-site tape backup only; Agfa PACS excluded from backup; no offsite copy; last restore test over 2 years ago; no BCP or DRP documented | 4 | 5 | 20 | CRITICAL | On-site tape backup operational for Napas HIS and SAP B1 only | IT Manager | Treat — include Agfa PACS in backup; conduct restore test immediately; implement offsite backup; document BCP/DRP | F-008 | Open

## Risk_Heatmap
Risk Heatmap ¦ Rawabi Health Services Co. ¦ RCA-P4-005
Likelihood × Impact Matrix — 25 Identified Risks ¦ CONFIDENTIAL
Likelihood → | Impact 1 (Negligible) | Impact 2 (Minor) | Impact 3 (Moderate) | Impact 4 (Major) | Impact 5 (Critical)
L5 — Almost Certain |  |  |  |  | R-008 R-011 R-018
L4 — Likely |  |  | R-013 | R-001 R-004 R-012 R-015 R-019 | R-009 R-022 R-025
L3 — Possible |  |  | R-003 R-007 R-014 R-020 | R-002 R-005 R-006 R-016 R-021 R-023 | R-017
L2 — Unlikely |  |  | R-010 R-024
L1 — Rare
Risk Rating Legend
CRITICAL |  | Score 20–25 — Immediate action required
HIGH |  | Score 12–19 — Action required within 30 days
MEDIUM |  | Score 6–11 — Action required within 90 days
LOW |  | Score 1–5 — Monitor; action at next review cycle

## Domain_Summary
Risk Summary by Domain ¦ Rawabi Health Services Co. ¦ RCA-P4-005
25 risks identified across 9 domains ¦ CONFIDENTIAL
Domain | Total Risks | Critical | High | Medium | Low | Top Risk
Governance & Strategy | 3 | 0 | 2 | 1 | 0 | R-001: Absence of cybersecurity strategy leads to uncoordinated con...
Access Control & Identity | 4 | 0 | 3 | 1 | 0 | R-004: Absence of MFA on Active Directory and Microsoft 365 enables...
Network Security | 3 | 2 | 0 | 1 | 0 | R-008: Flat network architecture enables unrestricted lateral movem...
Third-Party & Vendor | 4 | 1 | 2 | 1 | 0 | R-011: Uncontrolled Napas vendor remote access to live HIS — LIVE R...
Endpoint & Infrastructure | 3 | 0 | 3 | 0 | 0 | R-015: Unpatched Windows endpoints (41 of 180 on 2021 builds) expos...
Data Protection & Privacy | 4 | 1 | 2 | 1 | 0 | R-018: Processing patient health data without documented lawful bas...
Incident Response | 2 | 1 | 1 | 0 | 0 | R-022: Absence of incident response plan means cybersecurity incide...
Physical Security | 1 | 0 | 0 | 1 | 0 | R-024: Medina branch clinic operates without confirmed IT security ...
Business Continuity | 1 | 1 | 0 | 0 | 0 | R-025: No tested backup integrity or offsite recovery — ransomware ...
TOTAL | 25 | 5 | 8 | 9 | 3