## Cover
RESOLUTE COMPLIANCE ADVISORY LLP
Governance · Risk · Compliance
INFORMATION SECURITY RISK REGISTER
ISO 27001:2022 — Brightpath Technologies Pvt. Ltd.
Prepared for
Brightpath Technologies Pvt. Ltd.
IT Services · Bengaluru, India
Engagement Period: 02 October 2023 – 28 February 2024
Prepared by | kay Shahbaaz
Title | GRC Analyst
Date | 28 February 2024
Field | Details
Document Title | Information Security Risk Register
Document Ref | RCA-P1-005
Client | Brightpath Technologies Pvt. Ltd.
Source Assessment | RCA-P1-002 — ISO 27001:2022 Gap Assessment Report
Risk Methodology | Likelihood × Impact (1–5 scale); Score 1–25
Total Risks | 27
Prepared by | kay Shahbaaz
Date | 28 February 2024
Version | v1.0
Classification | CONFIDENTIAL
Status | Final
CONFIDENTIALITY NOTICE — This document is prepared exclusively for Brightpath Technologies Pvt. Ltd. and may not be disclosed without prior written consent of Resolute Compliance Advisory LLP.

## Risk Methodology
RISK ASSESSMENT METHODOLOGY
Brightpath Technologies Pvt. Ltd. · RCA-P1-005 · ISO 27001:2022
RISK SCORING FORMULA
Formula | Inherent Risk Score = Likelihood (L) × Impact (I)
Scale | Both Likelihood and Impact rated 1 to 5
Score Range | 1 (minimum) to 25 (maximum)
Residual Score | Residual Risk Score = Residual Likelihood × Residual Impact (after controls applied)
LIKELIHOOD SCALE
Rating | Score | Definition | Frequency
Very Low | 1 | Highly unlikely to occur in the foreseeable future | Less than once every 5 years
Low | 2 | Unlikely to occur but has happened in similar contexts | Once every 2–5 years
Medium | 3 | Possible — may occur under certain circumstances | Once per year
High | 4 | Likely — has occurred before or expected to occur | Multiple times per year
Very High | 5 | Near certain — occurs regularly or is actively exploited | Monthly or more frequent
IMPACT SCALE
Rating | Score | Definition | Business Impact
Negligible | 1 | Minimal disruption; no reputational or financial consequence | Operational inconvenience only
Minor | 2 | Limited impact; manageable without significant resource | Minor cost or effort to remediate
Moderate | 3 | Noticeable disruption to operations or client service delivery | Client notification may be required
Significant | 4 | Major disruption; potential client data breach or SLA breach | Regulatory, legal, or contractual exposure
Critical | 5 | Severe and potentially irreversible impact on the organisation | Regulatory action, litigation, or loss of clients
RISK RATING BANDS
Rating | Score Range | Definition | Response Requirement
Critical | 20 – 25 | Unacceptable risk requiring immediate escalation | Immediate action required — escalate to senior management
High | 12 – 19 | Significant risk requiring priority remediation | Remediate within 90 days — assign named owner
Medium | 6 – 11 | Moderate risk to be addressed in planned programme | Remediate within 180 days — include in risk treatment plan
Low | 1 – 5 | Acceptable or negligible risk — monitor and review | Accept with monitoring — review at next risk assessment
RISK TREATMENT OPTIONS
Treatment | Code | Definition | When Appropriate
Mitigate | M | Implement controls to reduce likelihood and/or impact to acceptable level | Most risks where controls are cost-effective and feasible
Accept | A | Acknowledge risk and accept without further treatment action | Low-rated risks or where cost of treatment exceeds potential loss
Transfer | T | Transfer risk to third party via insurance or contractual arrangement | Risks with high financial impact, particularly business continuity
Avoid | V | Eliminate risk by ceasing the activity or process that introduces it | Where risk cannot be reduced to acceptable level by other means

## Risk Register
RESOLUTE COMPLIANCE ADVISORY LLP · Information Security Risk Register · RCA-P1-005 · Brightpath Technologies Pvt. Ltd. | [13 empty] | CONFIDENTIAL
IDENTIFICATION | RISK DESCRIPTION |  |  |  | INHERENT RISK |  |  |  | TREATMENT |  | RESIDUAL RISK |  |  |  | MANAGEMENT
Risk ID | Domain | Asset / Process | Threat | Vulnerability | L | I | Score | Rating | Treatment | Control / Finding Ref | RL | RI | Score | Rating | Risk Owner | Target Date | Status
R-001 | Governance | ISMS Framework | Absence of formal information security governance | No information security policy, ISMS scope, or management accountability structure | 4 | 5 | 20 | Critical | Mitigate | F-001 / A.5.1 | 2 | 3 | 6 | Medium | CISO / IT Manager | Mar 2024 | Open
R-002 | Governance | Information Assets | Uncontrolled information assets | No formal asset inventory; assets unclassified and without assigned ownership | 4 | 4 | 16 | High | Mitigate | F-002 / A.5.9 | 2 | 3 | 6 | Medium | IT Manager | Mar 2024 | Open
R-003 | Governance | Risk Management | Absence of risk-driven security decisions | No risk assessment methodology, risk criteria, or documented risk treatment process | 4 | 5 | 20 | Critical | Mitigate | F-003 / Clause 6.1.2 | 2 | 3 | 6 | Medium | CISO / IT Manager | Mar 2024 | Open
R-004 | Governance | Compliance Monitoring | Non-compliance with ISO 27001:2022 certification requirements | Multiple foundational clauses unmet; organisation not eligible for certification audit | 4 | 4 | 16 | High | Mitigate | RCA-P1-002 / Multiple | 2 | 2 | 4 | Low | IT Manager | Sep 2024 | Open
R-005 | Access Control | AWS Production Environment | Unauthorised access to production systems | Developers hold persistent administrative access to production AWS without least-privilege enforcement | 4 | 5 | 20 | Critical | Mitigate | F-004 / A.5.15 / A.8.2 | 2 | 3 | 6 | Medium | IT Manager | Feb 2024 | Open
R-006 | Access Control | Former Employee Credentials | Unauthorised access by former employees | Active credentials identified for two former employees not revoked upon departure | 5 | 5 | 25 | Critical | Mitigate | F-004 / A.5.18 / A.6.5 | 1 | 3 | 3 | Low | IT Manager | Immediate | Open — Live Risk
R-007 | Access Control | Identity Lifecycle | Privilege creep and orphaned accounts | No formal access provisioning or periodic access review process; accounts accumulate excess rights | 3 | 4 | 12 | High | Mitigate | A.5.16 / A.5.17 / A.5.18 | 2 | 3 | 6 | Medium | IT Manager | Apr 2024 | Open
R-008 | Access Control | Authentication Controls | Account compromise via weak authentication | MFA not enforced on all AWS accounts; password complexity not formally mandated | 3 | 5 | 15 | High | Mitigate | A.8.5 | 1 | 4 | 4 | Low | IT Manager | Mar 2024 | Open
R-009 | Third-Party Risk | Supplier Ecosystem | Security breach via unvetted third-party vendor | No vendor security assessments conducted; security clauses absent from all supplier contracts | 3 | 5 | 15 | High | Mitigate | F-005 / A.5.19 / A.5.20 | 2 | 3 | 6 | Medium | IT Manager | May 2024 | Open
R-010 | Third-Party Risk | Cloud Service Provider (AWS) | Misconfiguration of cloud services | AWS shared responsibility model not formally documented; no cloud security baseline defined | 3 | 4 | 12 | High | Mitigate | A.5.23 | 2 | 3 | 6 | Medium | IT Manager | Apr 2024 | Open
R-011 | Third-Party Risk | ICT Supply Chain | Software supply chain compromise | Third-party software components used in development without formal security vetting | 2 | 4 | 8 | Medium | Mitigate | A.5.21 / A.8.25 | 1 | 3 | 3 | Low | Development Lead | Jun 2024 | Open
R-012 | Incident Management | Security Incident Handling | Uncontrolled security incident escalating to data breach | No incident response plan, severity classification, or defined escalation procedures | 3 | 5 | 15 | High | Mitigate | F-006 / A.5.24 / A.5.26 | 2 | 3 | 6 | Medium | IT Manager | Apr 2024 | Open
R-013 | Incident Management | Security Event Detection | Security events undetected or misclassified | No SIEM or structured log review process; CloudTrail logs not actively monitored | 3 | 4 | 12 | High | Mitigate | A.5.25 / A.8.15 / A.8.16 | 2 | 3 | 6 | Medium | IT Manager | May 2024 | Open
R-014 | Incident Management | Post-Incident Learning | Recurring incidents due to absence of lessons learned process | No post-incident review process or incident register maintained | 3 | 3 | 9 | Medium | Mitigate | A.5.27 | 2 | 2 | 4 | Low | IT Manager | Jun 2024 | Open
R-015 | People Security | Workforce — All Staff | Social engineering or phishing attack succeeds | No security awareness training; staff unprepared to identify or report threats | 4 | 4 | 16 | High | Mitigate | F-007 / A.6.3 | 2 | 3 | 6 | Medium | HR / IT Manager | Apr 2024 | Open
R-016 | People Security | New Hires | Insider threat from unverified personnel | No pre-employment background screening; staff with sensitive access not verified | 2 | 5 | 10 | Medium | Mitigate | F-008 / A.6.1 | 1 | 3 | 3 | Low | HR Manager | Mar 2024 | Open
R-017 | People Security | Remote Workers | Data exposure via insecure remote working | No remote working security policy; use of personal devices and unsecured networks uncontrolled | 3 | 4 | 12 | High | Mitigate | A.6.7 | 2 | 3 | 6 | Medium | IT Manager | May 2024 | Open
R-018 | Vulnerability Management | IT Infrastructure | Exploitation of unpatched systems | No vulnerability scanning programme; patches applied reactively; systems >90 days overdue | 3 | 5 | 15 | High | Mitigate | F-009 / A.8.8 | 2 | 3 | 6 | Medium | IT Manager | Mar 2024 | Open
R-019 | Vulnerability Management | Network Infrastructure | Lateral movement via unsegregated network | Production and development environments not formally segregated at network level | 3 | 4 | 12 | High | Mitigate | A.8.22 | 2 | 3 | 6 | Medium | IT Manager | May 2024 | Open
R-020 | Vulnerability Management | Configuration Baseline | Exploitation of misconfigured systems | No configuration management baselines or hardening standards defined | 3 | 4 | 12 | High | Mitigate | A.8.9 | 2 | 2 | 4 | Low | IT Manager | May 2024 | Open
R-021 | Secure Development | Client-Facing Applications | Vulnerable software delivered to US clients | No secure SDLC; no security testing prior to deployment; OWASP Top 10 not addressed | 3 | 5 | 15 | High | Mitigate | F-010 / A.8.25 / A.8.26 / A.8.29 | 2 | 3 | 6 | Medium | Development Lead | Jun 2024 | Open
R-022 | Secure Development | Source Code | Unauthorised access to or theft of source code | GitHub access not formally reviewed; no policy on access to source code repositories | 2 | 4 | 8 | Medium | Mitigate | A.8.4 | 1 | 3 | 3 | Low | Development Lead | May 2024 | Open
R-023 | Secure Development | Test Environments | Exposure of production data in test environments | Production data used in test environments without masking or anonymisation | 3 | 4 | 12 | High | Mitigate | A.8.33 | 1 | 2 | 2 | Low | Development Lead | May 2024 | Open
R-024 | Business Continuity | IT Systems / Client Services | Service disruption causing client SLA breach | No BCP or DRP; AWS backups untested; no defined RTO or RPO for any system | 3 | 5 | 15 | High | Mitigate | A.5.29 / A.5.30 / A1.3 | 2 | 3 | 6 | Medium | IT Manager | Jun 2024 | Open
R-025 | Business Continuity | Critical Personnel | Key person dependency — loss of critical IT staff | Insufficient documented operating procedures; IT knowledge concentrated in one or two individuals | 2 | 4 | 8 | Medium | Mitigate | A.5.37 | 2 | 3 | 6 | Medium | Head of Operations | Jul 2024 | Open
R-026 | Data Protection | Client Personal Data | Unauthorised disclosure or loss of client personal data | No DLP controls; no data classification; no encryption policy; client data inadequately protected | 3 | 5 | 15 | High | Mitigate | A.5.12 / A.8.11 / A.8.12 / A.8.24 | 2 | 3 | 6 | Medium | IT Manager | Jun 2024 | Open
R-027 | Data Protection | Storage Media | Data leakage via improper media disposal | No formal media disposal or sanitisation procedure; old hardware not formally decommissioned | 2 | 4 | 8 | Medium | Mitigate | A.7.10 / A.7.14 | 1 | 2 | 2 | Low | IT Manager | Jun 2024 | Open

## Summary Dashboard
RISK REGISTER — SUMMARY DASHBOARD
Brightpath Technologies Pvt. Ltd. · RCA-P1-005 · 28 February 2024
OVERALL RISK SUMMARY
Total Risks | Critical | High | Medium | Low | Live Risks
27 | 4 | 17 | 6 | 0 | 1
INHERENT RISK vs RESIDUAL RISK — BY RATING
Rating | Inherent Count | Residual Count | Risk Reduction
Critical | 4 | 0 | 4
High | 17 | 0 | 17
Medium | 6 | 17 | -11
Low | 0 | 10 | -10
RISK COUNT BY DOMAIN
Domain | Total | Critical | High | Medium | Low
Governance | 4 | 2 | 2 | 0 | 0
Access Control | 4 | 2 | 2 | 0 | 0
Third-Party Risk | 3 | 0 | 2 | 1 | 0
Incident Management | 3 | 0 | 2 | 1 | 0
People Security | 3 | 0 | 2 | 1 | 0
Vulnerability Management | 3 | 0 | 3 | 0 | 0
Secure Development | 3 | 0 | 2 | 1 | 0
Business Continuity | 2 | 0 | 1 | 1 | 0
Data Protection | 2 | 0 | 1 | 1 | 0
TOTAL | 27 | 4 | 17 | 6 | 0
RISK TREATMENT BREAKDOWN
Treatment | Count | % of Total
Mitigate | 27 | 100%
Accept | 0 | 0%
Transfer | 0 | 0%
Avoid | 0 | 0%