## Cover
RESOLUTE COMPLIANCE ADVISORY LLP
Governance · Risk · Compliance
UPDATED RISK REGISTER
NCA ECC-2:2024 Delta Assessment — Al Ameen Insurance Company — RCA-P3C-004
| Document Title | Updated Risk Register — NCA ECC-2:2024 Delta Assessment
| Document Ref | RCA-P3C-004
| Client | Al Ameen Insurance Company
| Project | NCA ECC-2:2024 Delta Assessment — Returning Engagement
| Baseline Ref | RCA-P3-004 (Project 3 Risk Register, October 2024)
| Prepared by | kay Shahbaaz, GRC Auditor
| Reviewed by | Resolute Compliance Advisory LLP
| Date Issued | 15 April 2025
| Version | v1.0
| Classification | CONFIDENTIAL
| Status | Final
RISK METHODOLOGY
| Scoring Method | Likelihood × Impact (L × I) on a 1–5 scale. Risk Score = L × I. Range: 1–25.
| Likelihood Scale | 1 = Rare ¦ 2 = Unlikely ¦ 3 = Possible ¦ 4 = Likely ¦ 5 = Almost Certain
| Impact Scale | 1 = Negligible ¦ 2 = Minor ¦ 3 = Moderate ¦ 4 = Significant ¦ 5 = Catastrophic
| Critical (20–25) | Immediate action required. Escalate to Board. Treatment within 30 days.
| High (12–19) | Priority action required. Treatment within 60 days. Senior management oversight.
| Medium (6–11) | Planned treatment required. Treatment within 90 days. Management monitoring.
| Low (1–5) | Monitor and review. Treatment within 180 days or accept with documented rationale.
STATUS LEGEND
| Open | Risk is active. Treatment plan not yet implemented.
| In Treatment | Risk treatment actions are in progress.
| Closed | Risk resolved. Treatment implemented and verified.
| Accepted | Residual risk formally accepted by senior management.
| New | Risk identified in this delta assessment (not in RCA-P3-004).
CONFIDENTIAL — RESOLUTE COMPLIANCE ADVISORY LLP — RCA-P3C-004 — v1.0

## Risk Register
UPDATED RISK REGISTER — Al Ameen Insurance Company — RCA-P3C-004 — 15 April 2025
Baseline: RCA-P3-004 (October 2024) — 28 risks ¦ Current: 33 risks (28 retained + 5 new delta gaps) ¦ Methodology: L × I (1–5 scale)
Risk ID | Status | Domain | Risk Description | Baseline L | Baseline I | Baseline Score | Baseline Rating | Current L | Current I | Current Score | Current Rating | Control Gap / Cause | Treatment Action | Risk Owner | Finding Ref
GOVERNANCE
R-001 | In Treatment | Governance | Absence of a mature cybersecurity governance framework — cybersecurity strategy not fully embedded; IT Security Manager in post but governance structure not yet complete | 5 | 5 | 25 | Critical | 4 | 4 | 16 | High | Top-level policy ratified (CA-005) but cybersecurity strategy KPIs, board reporting cycle, and supporting procedures not yet formalised | Complete cybersecurity strategy with KPIs (CA-030). Establish quarterly board cybersecurity reporting. Complete supporting policy suite (CA-005 Phase 2). | IT Security Manager | F-001 / RF
R-002 | In Treatment | Governance | Cybersecurity risk assessment process not yet complete — formal risk register not produced from first assessment cycle | 5 | 4 | 20 | Critical | 3 | 4 | 12 | High | Risk assessment workshops commenced (CA-010) but not complete. Risk register not yet produced from the new assessment cycle. | Complete first formal risk assessment cycle (CA-010). Produce risk register by March 2025. Establish annual review cycle. | IT Security Manager | F-003
R-003 | In Treatment | Governance | Role-based cybersecurity training not delivered — awareness session delivered to all staff but IT and system administrator role-specific training absent | 4 | 3 | 12 | High | 4 | 3 | 12 | High | General awareness session completed (CA-006). Role-based training for IT Operations, system administrators, and IT Security Manager not scheduled. | Deliver role-based cybersecurity training for all IT and administrative staff (CA-016). Establish annual training calendar. | IT Security Manager | F-006
R-004 | Open | Governance | No quantum-readiness roadmap — cryptographic algorithms deployed across Oracle Insurance and Azure workloads not assessed for quantum vulnerability | 2 | 4 | 8 | Medium | 2 | 4 | 8 | Medium | ECC-2:2024 new requirement (1-6-3). No cryptographic inventory exists. Quantum-readiness assessment not initiated. | Complete cryptographic inventory (CA-031). Develop quantum-readiness roadmap (CA-035) by July 2025. | IT Security Manager | DG-005
IDENTITY & ACCESS MANAGEMENT
R-005 | Closed | Identity & Access Management | Shared Oracle Insurance production system administrator credentials — unmanaged shared account with full production system access used by multiple administrators | 5 | 5 | 25 | Critical | 1 | 1 | 1 | Low | RESOLVED: Shared account 'oracle_admin' deactivated (CA-002). Three individual named accounts provisioned. Evidence: EV-002. This risk is closed. | Risk closed — corrective action CA-002 complete. Monitor at next annual review. | IT Operations Manager | F-007 (Closed)
R-006 | In Treatment | Identity & Access Management | Privileged access management gaps — PAM solution not deployed; service accounts not fully inventoried; Oracle Insurance and Guidewire service accounts not subject to formal review | 4 | 4 | 16 | High | 3 | 4 | 12 | High | Azure AD privileged accounts reviewed (CA-015). Oracle Insurance and Guidewire service accounts not inventoried. No PAM solution deployed. | Deploy PAM solution or equivalent (CA-022 Phase 3). Complete service account inventory across Oracle Insurance and Guidewire. | IT Operations Manager | F-007
R-007 | In Treatment | Identity & Access Management | Incomplete MFA coverage — MFA enforced on Azure AD privileged accounts but not yet extended to all user accounts or Oracle Insurance application-level access | 4 | 4 | 16 | High | 3 | 3 | 9 | Medium | Azure AD MFA for privileged accounts complete (CA-003). General user MFA not enforced. Oracle Insurance has no MFA capability at application level. | Extend MFA to all Azure AD user accounts. Assess Oracle Insurance MFA options with vendor. | IT Operations Manager | F-007
VULNERABILITY MANAGEMENT
R-008 | Open | Vulnerability Management | No vulnerability management programme — no scanning conducted, no patching schedule, no SLA for remediation of critical vulnerabilities across Oracle Insurance, Guidewire, Azure, and network infrastructure | 5 | 4 | 20 | Critical | 4 | 4 | 16 | High | Tenable.io procured (CA-013 In Progress). No scans conducted. Patch management ad hoc. Critical vulnerabilities may exist on Oracle Insurance (6-year-old deployment) and Guidewire. | Deploy Tenable.io (CA-013). Conduct initial scan of all critical systems. Establish patching SLA: Critical 15 days, High 30 days (CA-017). | IT Operations Manager | F-008
R-009 | Open | Vulnerability Management | Oracle Insurance production system unpatched — version deployed in 2019 with no documented patching history; potential accumulation of unaddressed security vulnerabilities | 5 | 5 | 25 | Critical | 4 | 5 | 20 | Critical | No vulnerability scans conducted on Oracle Insurance. No patching log available. System critical to motor and medical insurance operations. | Include Oracle Insurance in first Tenable.io scan cycle. Engage Oracle vendor for patch status and security advisory review. Document patching history. | IT Operations Manager | F-008
INCIDENT RESPONSE
R-010 | Open | Incident Response | No incident response capability — no IRP, no response team, no NCA/SAMA notification procedure; Al Ameen cannot respond to or report a cybersecurity incident in a structured manner | 5 | 5 | 25 | Critical | 5 | 5 | 25 | Critical | IRP not drafted (CA-014 Not Started). No designated response team. Regulatory notification obligations to NCA and SAMA unmet. This is the highest active risk in the current register. | Draft and approve IRP as Phase 2 priority (CA-014). Designate incident response team. Conduct tabletop exercise (CA-021). Target: IRP approved by 30 June 2025. | IT Security Manager | RF-001 / F-009
R-011 | Open | Incident Response | Regulatory incident notification capability absent — no documented process to notify NCA and SAMA within required timeframes following a confirmed cybersecurity incident | 5 | 4 | 20 | Critical | 5 | 4 | 20 | Critical | IRP not drafted. NCA and SAMA notification timelines not documented. Failure to notify within required timeframes is a separate regulatory breach. | Include NCA and SAMA notification procedures in IRP (CA-014). Identify regulatory notification contacts and timelines. Test notification process in tabletop exercise. | IT Security Manager | RF-001
BUSINESS CONTINUITY & DR
R-012 | Open | Business Continuity & DR | No BCP or DRP — Al Ameen has no documented or tested capability to recover Oracle Insurance or Guidewire following a cybersecurity incident or system failure | 5 | 5 | 25 | Critical | 5 | 5 | 25 | Critical | BCP and DRP not initiated (CA-019, CA-029 Not Started). On-site tape backup only. No off-site backup. No defined RTO or RPO for any critical system. | Define RTO/RPO targets for Oracle Insurance and Guidewire. Implement off-site backup. Develop BCP and DRP (CA-019, CA-029). Conduct DRP test. | IT Operations Manager | RF-002 / F-005
R-013 | Open | Business Continuity & DR | On-site tape backup only — no off-site or cloud backup for Oracle Insurance, Guidewire, or PACS data; single point of failure in Riyadh DC | 4 | 5 | 20 | Critical | 4 | 5 | 20 | Critical | All backups on-site tape. Riyadh DC physical disaster or ransomware would result in permanent data loss. Backup integrity testing not conducted. | Implement cloud or off-site backup as emergency Phase 2 action. Conduct backup integrity test for all critical systems within 30 days. | IT Operations Manager | F-005
THIRD-PARTY MANAGEMENT
R-014 | Open | Third-Party Management | No cybersecurity security clauses in Najm contract — motor claims data exchange with no incident notification, right-to-audit, or data residency obligations | 4 | 4 | 16 | High | 4 | 4 | 16 | High | Najm contract reviewed — no security clauses. ECC-2:2024 localised vendor governance requirement (4-2-2) not met. CA-011 Not Started. | Execute cybersecurity addendum with Najm (CA-032). Include: cybersecurity obligations, incident notification (24hr), right-to-audit, data residency confirmation. | IT Security Manager | DG-002 / F-004
R-015 | Open | Third-Party Management | No cybersecurity security clauses in Shafafiyah contract — SAMA regulatory reporting data exchange with no security obligations | 4 | 4 | 16 | High | 4 | 4 | 16 | High | Shafafiyah contract reviewed — no security clauses. Shafafiyah interfaces with SAMA on behalf of Al Ameen — a compromise could affect regulatory reporting integrity. | Execute cybersecurity addendum with Shafafiyah (CA-032). Include: cybersecurity obligations aligned to SAMA requirements, incident notification, right-to-audit. | IT Security Manager | DG-002 / F-004
R-016 | Open | Third-Party Management | Reinsurance partner supply chain risk not assessed — Munich Re and Swiss Re receive policyholder PII and claims data with no cybersecurity obligations in reinsurance treaties | 3 | 4 | 12 | High | 3 | 4 | 12 | High | No supply chain cybersecurity risk assessment conducted for Munich Re or Swiss Re. No cybersecurity provisions in reinsurance treaties. Data includes policyholder PII. | Conduct supply chain risk assessment for Munich Re and Swiss Re (CA-033). Include cybersecurity data processing obligations in treaty addenda. | IT Security Manager | DG-003
R-017 | In Treatment | Third-Party Management | Third-party risk management framework absent — no formal process to assess, onboard, or monitor third-party cybersecurity posture | 5 | 4 | 20 | Critical | 4 | 4 | 16 | High | CA-008 In Progress — consultant engaged, framework not yet produced. Najm, Shafafiyah, Munich Re, and Swiss Re not subject to formal cybersecurity due diligence. | Complete third-party risk framework (CA-008). Apply framework to all critical third parties. Conduct first annual review cycle. | IT Security Manager | F-004
CLOUD SECURITY
R-018 | Open | Cloud Security | No cloud security baseline for Azure KSA workloads — no documented configuration baseline, no CSPM tool, no cloud security posture visibility | 4 | 4 | 16 | High | 4 | 4 | 16 | High | Azure cloud access MFA now enforced (CA-003) but no cloud security baseline documented. No CSPM tools deployed. Azure Sentinel provisioned but not fully operational. | Document cloud security baseline for Azure KSA workloads aligned to ECC-2:2024 4-3-1. Deploy CSPM capability. Complete Azure Sentinel alert configuration. | IT Operations Manager / Azure Admin | DG — Cloud
LOG MANAGEMENT
R-019 | Closed | Log Management | Log retention below SAMA minimum — logs retained for 30 days only against SAMA requirement of 12 months | 5 | 4 | 20 | Critical | 1 | 1 | 1 | Low | RESOLVED: Log retention extended to 365 days across Azure Monitor and Log Analytics workspaces (CA-004). Evidence: EV-004. This risk is closed. | Risk closed — CA-004 complete. Monitor at next annual review. | Azure Admin | F-010 (Closed)
R-020 | In Treatment | Log Management | SIEM capability not fully operational — Azure Sentinel provisioned but alert rules not fully configured; SIEM not yet providing active threat detection | 4 | 4 | 16 | High | 3 | 3 | 9 | Medium | Azure Sentinel workspace provisioned (CA-020 In Progress). Log sources connected. Alert rules configuration incomplete. No active monitoring output yet. | Complete Azure Sentinel alert rule configuration (CA-020). Define monitoring use cases. Establish alert triage process for IT Security Manager. | Azure Admin | F-010
CRYPTOGRAPHIC CONTROLS
R-021 | New | Cryptographic Controls | No cryptographic controls policy or inventory — certificates, keys, and algorithms across Oracle Insurance, Guidewire, and Azure not inventoried or governed | 3 | 4 | 12 | High | 3 | 4 | 12 | High | New ECC-2:2024 requirement (1-6-1, 1-6-2). No cryptographic inventory exists. Certificate expiry risk on production systems not assessed. | Establish cryptographic controls policy and conduct cryptographic asset discovery (CA-031). Target: 31 May 2025. | IT Security Manager | DG-001
R-022 | New | Cryptographic Controls | Certificate expiry risk — unknown certificate lifecycle status across Oracle Insurance and Guidewire production systems; unmanaged expiry could cause unplanned outages | 3 | 5 | 15 | High | 3 | 4 | 12 | High | No cryptographic inventory exists (DG-001). Certificate expiry dates on Oracle Insurance and Guidewire unknown. Production outage risk if certificates expire undetected. | Conduct emergency certificate discovery on Oracle Insurance and Guidewire. Implement automated certificate expiry alerting. Include in CA-031 scope. | IT Operations Manager | DG-001
NETWORK SECURITY
R-023 | Open | Network Security | No network segmentation — corporate and operational network traffic not segregated; a compromise of a user endpoint could provide lateral movement to Oracle Insurance production environment | 4 | 5 | 20 | Critical | 4 | 5 | 20 | Critical | Flat network confirmed. No segmentation between user workstations, Oracle Insurance production, and Guidewire. CA-022 (network segmentation) Phase 3, Not Started. | Implement network segmentation as Phase 3 priority (CA-022). Separate Oracle Insurance production, Guidewire, user network, and DMZ segments. Deploy IDS/IPS. | IT Operations Manager | F — Network
ENDPOINT SECURITY
R-024 | Open | Endpoint Security | No EDR deployed — anti-malware only on endpoints; no behavioural detection, no endpoint visibility on servers hosting Oracle Insurance and Guidewire | 4 | 4 | 16 | High | 4 | 4 | 16 | High | Anti-malware deployed. EDR not deployed (CA-023 Not Started). Oracle Insurance and Guidewire servers have no advanced endpoint protection. | Deploy EDR on all critical servers and endpoints (CA-023). Target: Phase 3 (May–July 2025). | IT Operations Manager | F-008
SECURITY AWARENESS
R-025 | In Treatment | Security Awareness | Security awareness programme not embedded — one all-staff session delivered; annual training cycle not established; 19 non-attendees not yet reached | 4 | 3 | 12 | High | 3 | 3 | 9 | Medium | Initial session delivered December 2024 (CA-006). 271/290 attended. Make-up session scheduled March 2025. Annual programme not established (CA-027 Phase 4). | Deliver make-up session for 19 non-attendees (March 2025). Establish annual awareness programme with completion tracking (CA-027). | IT Security Manager | F-006
APPLICATION SECURITY
R-026 | Open | Application Security | No application security controls — no WAF on internet-facing applications, no application-level audit logging on Oracle Insurance, no secure SDLC | 4 | 4 | 16 | High | 4 | 4 | 16 | High | No WAF deployed. Oracle Insurance application-level audit logging not enabled. No secure development practices documented. ECC-2:2024 2-6-1 to 2-6-4 Non-Conformant. | Deploy WAF for internet-facing applications. Enable Oracle Insurance application-level audit logging. Define secure SDLC baseline. | IT Operations Manager | F — AppSec
THREAT INTELLIGENCE
R-027 | New | Threat Intelligence | No threat intelligence capability — Al Ameen does not consume NCA threat intelligence feeds or sector-specific threat advisories | 3 | 4 | 12 | High | 3 | 4 | 12 | High | New ECC-2:2024 requirement (3-4-1, 3-4-2). No threat intelligence function. Emerging threats relevant to Saudi insurance sector not actioned. | Subscribe to NCA threat intelligence feeds (CA-034). Assign IT Security Manager as threat intel owner. Integrate into vulnerability management process. | IT Security Manager | DG-004
REGULATORY COMPLIANCE
R-028 | Open | Regulatory Compliance | ECC-2:2024 transition — Al Ameen's overall ECC-2:2024 conformance at 39%; risk of regulatory scrutiny from NCA or SAMA if conformance improvement is not demonstrable | 3 | 5 | 15 | High | 3 | 4 | 12 | High | ECC-2:2024 effective from October 2024. Current conformance 39%. No formal NCA engagement plan. SAMA oversight of cybersecurity compliance for regulated insurers. | Develop NCA engagement plan. Document remediation roadmap for SAMA. Target 60% conformance by October 2025 (CA-030). | IT Security Manager | —
PERSONNEL SECURITY
R-029 | In Treatment | Personnel Security | IT Security Manager newly appointed — single point of dependency; institutional knowledge of cybersecurity programme concentrated in one individual | 3 | 4 | 12 | High | 3 | 3 | 9 | Medium | IT Security Manager appointed January 2025. No deputy. Limited cybersecurity team. Programme continuity risk if IT Security Manager departs. | Document cybersecurity programme governance. Cross-train IT Operations Manager on key cybersecurity processes. Define succession plan. | IT Director | —
SUPPLY CHAIN
R-030 | New | Supply Chain | Software supply chain integrity not verified — Oracle Insurance and Guidewire software updates deployed without integrity verification; risk of supply chain compromise | 2 | 5 | 10 | Medium | 2 | 5 | 10 | Medium | New ECC-2:2024 requirement (1-7-2). No code signing verification or software bill of materials for critical application updates. | Implement software supply chain integrity controls (CA-033). Verify Oracle and Guidewire software update authenticity. Establish vendor security advisory review process. | IT Operations Manager | DG-003
DATA SECURITY
R-031 | Open | Data Security | No data classification scheme — policyholder PII, claims data, and commercially sensitive reinsurance cession data not classified or subject to formal handling requirements | 4 | 4 | 16 | High | 4 | 4 | 16 | High | No data classification policy (CA-026 Not Started). Policyholder PII and health-related claims data processed without formal classification or handling controls. | Develop and implement data classification scheme (CA-026). Apply classification to Oracle Insurance and Guidewire data stores. | IT Security Manager | —
DATA PRIVACY
R-032 | Open | Data Privacy | PDPL exposure — Al Ameen processes Saudi national policyholder personal data; no PDPL compliance programme initiated; SDAIA enforcement active | 3 | 5 | 15 | High | 3 | 5 | 15 | High | PDPL enforcement fully active 2024. Al Ameen processes policyholder names, national IDs, health claims data. No PDPL assessment conducted. Note: PDPL not in scope of this engagement but flagged for awareness. | Initiate PDPL compliance assessment as a separate engagement. This risk is flagged for Board awareness — outside ECC-2:2024 scope but represents significant regulatory exposure. | IT Security Manager / Legal | — (out of scope)
PHYSICAL SECURITY
R-033 | Closed | Physical Security | Data centre physical access controls — multi-factor physical access and CCTV confirmed in Riyadh DC; physical security controls adequate | 2 | 4 | 8 | Medium | 2 | 3 | 6 | Medium | Physical access log and CCTV retention confirmed during fieldwork (EV-022). Riyadh DC physical controls conformant. Risk downgraded. | Monitor at next annual review. No further treatment required at this time. | IT Operations Manager | — (Closed)

## Risk Heatmap
RISK HEATMAP — Al Ameen Insurance Company — ECC-2:2024 Delta Assessment — April 2025
Current risk scores (post-Phase 1 remediation) ¦ Axes: Likelihood (1–5) × Impact (1–5) ¦ Score = L × I
I↑ / L→ | L=1 | L=2 | L=3 | L=4 | L=5
I=5 |  | R-030 | R-032 | R-009, R-013, R-023 | R-010, R-012
I=4 |  | R-004 | R-002, R-006, R-016, R-021, R-022, R-027, R-028 | R-001, R-008, R-014, R-015, R-017, R-018, R-024, R-026, R-031 | R-011
I=3 |  | R-033 | R-007, R-020, R-025, R-029 | R-003
I=2
I=1 | R-005, R-019
LEGEND
Critical (20–25)
High (12–19)
Medium (6–11)
Low (1–5)
RISK MOVEMENT SUMMARY — Oct 2024 vs Apr 2025
Risk R-005 (Shared Oracle Creds) | CLOSED | Critical (25) → Closed
Risk R-019 (Log Retention) | CLOSED | High (20) → Closed
Risk R-033 (Physical Security) | IMPROVED | High (8) → Low (6)
Risks R-021, R-022, R-027, R-030 | NEW | New delta gaps from ECC-2:2024
Risk R-010 (No IRP) | OPEN | Critical (25) → Critical (25) — no progress
Risk R-012 (No BCP/DRP) | OPEN | Critical (25) → Critical (25) — no progress

## Dashboard
RISK DASHBOARD — Al Ameen Insurance Company — RCA-P3C-004 — 15 April 2025
Summary view of risk profile movement from Project 3 baseline (October 2024) to current assessment (April 2025)
| Total Risks | Critical | High | Medium | Low / Closed | New Risks (ECC-2)
| 33 | 5 | 12 | 9 | 7 | 5
| 28 retained + 5 new | Down from 9 baseline | Stable | Up (new delta gaps) | 2 risks closed | Delta gap additions
RISK STATUS BREAKDOWN — CURRENT (APRIL 2025)
| Open | In Treatment | Closed | New | Accepted | Total
| 16 | 9 | 2 | 5 | 0 | 32
RISK COUNT BY DOMAIN — CURRENT VS BASELINE
| Domain | Baseline (P3) | Current | Change | Highest Current Risk | Status
| Governance | 4 | 4 | = | R-002 High (12) | In Treatment
| Identity & Access Mgmt | 5 | 3 | ↓2 | R-006 High (12) | In Treatment
| Vulnerability Mgmt | 3 | 2 | = | R-009 Critical (20) | Open
| Incident Response | 2 | 2 | = | R-010 Critical (25) | Open
| Business Continuity | 3 | 2 | = | R-012 Critical (25) | Open
| Third-Party Mgmt | 4 | 4 | = | R-014/015 High (16) | Open
| Cloud Security | 2 | 1 | ↓1 | R-018 High (16) | Open
| Log Management | 2 | 2 | ↓1 | R-020 Medium (9) | In Treatment
| Cryptographic Controls | 0 | 2 | ↑2 | R-022 High (12) — New | New
| Network Security | 1 | 1 | = | R-023 High (20) | Open
| Endpoint Security | 1 | 1 | = | R-024 High (16) | Open
| Security Awareness | 1 | 1 | = | R-025 Medium (9) | In Treatment
| Application Security | 0 | 1 | ↑1 | R-026 High (16) | Open
| Threat Intelligence | 0 | 1 | ↑1 | R-027 High (12) — New | New
| Regulatory Compliance | 0 | 1 | ↑1 | R-028 High (15) | Open
| Personnel Security | 0 | 1 | ↑1 | R-029 Medium (9) | In Treatment
| Supply Chain | 0 | 1 | ↑1 | R-030 High (10) — New | New
| Data Security | 0 | 1 | ↑1 | R-031 High (16) | Open
| Data Privacy | 0 | 1 | ↑1 | R-032 High (15) — Flag | Open
| Physical Security | 1 | 1 | ↓1 | R-033 Closed | Closed
PROJECT 3 BASELINE: 28 risks ¦ CURRENT: 33 risks (5 new ECC-2:2024 gaps) ¦ 2 risks CLOSED (R-005 Oracle creds, R-019 log retention) ¦ 1 Critical live risk CLOSED ¦ 5 Critical/High open risks requiring immediate action