## Dashboard
RESOLUTE COMPLIANCE ADVISORY LLP ¦ CORRECTIVE ACTION PLAN
RCA-P4-006 · Rawabi Health Services Co. · NCA ECC-1:2018 + PDPL Compliance Audit · CONFIDENTIAL
Client |  | Rawabi Health Services Co.
Audit Period |  | 10 November 2024 – 31 January 2025
CAP Period |  | December 2024 – October 2025
Frameworks |  | NCA ECC-1:2018 ¦ Saudi PDPL
Lead Auditor |  | kay Shahbaaz ¦ GRC Auditor
Document Ref |  | RCA-P4-006 ¦ v1.0 ¦ CONFIDENTIAL
Summary by Phase
Phase | Period | Actions | ECC Actions | PDPL Actions | Priority
Phase 1 — Critical Containment | Dec 2024 – Jan 2025 | 8 | 5 | 3 | CRITICAL
Phase 2 — Governance Build | Feb – Apr 2025 | 11 | 7 | 4 | HIGH
Phase 3 — Operational Controls | May – Jul 2025 | 8 | 5 | 3 | MEDIUM
Phase 4 — Sustain & Embed | Aug – Oct 2025 | 5 | 3 | 2 | LOW
TOTAL | Dec 2024 – Oct 2025 | 32 | 20 | 12 | —
Summary by Framework & Severity
Framework | Critical | High | Medium | Low | Total
NCA ECC-1:2018 | 4 | 7 | 6 | 3 | 20
Saudi PDPL | 2 | 2 | 5 | 3 | 12
TOTAL | 6 | 9 | 11 | 6 | 32

## Corrective_Actions
Corrective Action Plan ¦ Rawabi Health Services Co. ¦ NCA ECC-1:2018 + PDPL ¦ RCA-P4-006
CAP Period: December 2024 – October 2025 · Lead Auditor: kay Shahbaaz · CONFIDENTIAL
Action ID | Finding Ref | Framework | Priority | Corrective Action | Implementation Guidance | Responsible Owner (Client) | Target Completion | Effort Estimate | Status | Verification
PHASE 1 — CRITICAL CONTAINMENT ¦ December 2024 – January 2025
CA-001 | F-003 | ECC | CRITICAL | Rotate Napas HIS shared administrative credential immediately | Generate a new strong password (minimum 20 characters, mixed case, numbers, symbols) for the Napas HIS admin account. Distribute to authorised IT staff only via a password manager. Document the rotation date and schedule quarterly rotation going forward. | IT Manager | January 2025 | 1–2 days | Open | Pending completion and auditor sign-off
CA-002 | F-003 | ECC | CRITICAL | Implement dedicated VPN tunnel or jump server for all Napas vendor remote access sessions | Procure or configure a dedicated VPN solution or jump server for vendor access. Napas vendor must connect exclusively through this channel. Disable direct internet access to the HIS admin port. Document the access architecture. | IT Manager | January 2025 | 1–2 weeks | Open | Pending completion and auditor sign-off
CA-003 | F-003 | ECC | CRITICAL | Enable session logging and recording for all Napas vendor remote access | Configure the VPN or jump server to log all session start/end times, commands executed, and files accessed during vendor sessions. Retain logs for minimum 12 months. Assign IT staff responsibility for weekly log review. | IT Manager | January 2025 | 3–5 days | Open | Pending completion and auditor sign-off
CA-004 | F-003 / P-002 | ECC + PDPL | CRITICAL | Issue data protection addendum to Napas vendor support contract | Draft and execute a contractual addendum covering: data protection obligations, prohibition on retention of patient data beyond support session, breach notification obligation to Rawabi within 24 hours, and audit right for Rawabi. Engage legal counsel if required. | COO / Legal | January 2025 | 1–2 weeks | Open | Pending completion and auditor sign-off
CA-005 | F-008 | ECC | HIGH | Include Agfa PACS DICOM imaging data in backup schedule immediately | Configure the existing backup solution to include the Agfa PACS data store. Verify backup job completion within 48 hours of configuration. Update backup policy documentation to reflect the expanded scope. | IT Manager | December 2024 | 2–3 days | Open | Pending completion and auditor sign-off
CA-006 | F-008 | ECC | HIGH | Conduct documented restore test for Napas HIS backup data | Execute a full restore of the most recent Napas HIS backup to a test environment or isolated partition. Document the test date, backup version restored, data integrity check results, and restore time. Sign off by IT Manager. | IT Manager | January 2025 | 1–2 days | Open | Pending completion and auditor sign-off
CA-007 | P-001 | PDPL | CRITICAL | Design and implement PDPL-compliant patient consent form for all registration touchpoints | Draft a consent form disclosing: controller identity, processing purposes, data categories, third-party recipients (Bupa Arabia, Nphies, Al Bilad Lab), retention periods, and patient rights. Have reviewed by legal counsel. Deploy at Jeddah and Medina registration desks. Implement consent record retention process in Napas HIS. | COO / Legal | January 2025 | 2–3 weeks | Open | Pending completion and auditor sign-off
CA-008 | P-001 | PDPL | CRITICAL | Map all data processing activities to PDPL lawful bases | Document the lawful basis for each processing activity identified in the data processing overview: patient registration (consent), Nphies submission (legal obligation under MoH mandate), Bupa Arabia sharing (consent/contract), Al Bilad Lab (consent/contract), staff HR (contract). Engage legal counsel to validate the assessment. Retain as evidence of PDPL compliance. | COO / Legal | January 2025 | 1–2 weeks | Open | Pending completion and auditor sign-off
PHASE 2 — GOVERNANCE BUILD ¦ February – April 2025
CA-009 | F-001 | ECC | CRITICAL | Appoint cybersecurity lead with defined authority and accountability | Designate the IT Manager as interim cybersecurity lead with formal mandate pending CISO recruitment. Define the role in writing: responsibilities, reporting line (to COO), authority to enforce security controls, and budget access. Consider external CISO advisory support for the remediation period. | COO | February 2025 | 1 week | Open | Pending completion and auditor sign-off
CA-010 | F-001 | ECC | CRITICAL | Draft and obtain executive approval for Information Security Policy | Develop an Information Security Policy covering: scope, objectives, roles and responsibilities, control obligations aligned to ECC-1:2018, acceptable use, and incident reporting. Obtain formal approval from the COO or equivalent. Communicate to all staff. Review annually. | IT Manager / COO | March 2025 | 2–3 weeks | Open | Pending completion and auditor sign-off
CA-011 | F-002 | ECC | CRITICAL | Conduct cybersecurity risk assessment and establish risk register | Adopt Likelihood × Impact methodology (1–5 scale). Conduct formal risk assessment covering all critical systems: Napas HIS, Agfa PACS, SAP B1, Active Directory, Microsoft 365, and third-party relationships. Document risks in a risk register with owners and treatment decisions. Schedule annual review and event-driven reassessment. | IT Manager | March 2025 | 2–3 weeks | Open | Pending completion and auditor sign-off
CA-012 | F-005 | ECC | HIGH | Develop and approve Cybersecurity Incident Response Plan | Develop IR Plan covering: incident classification matrix (including PDPL breach classification), roles and responsibilities, containment and eradication procedures, SDAIA 72-hour notification procedure, patient notification process for high-risk breaches, escalation contacts, and post-incident review process. Designate IR team. Conduct tabletop exercise within 30 days of approval. | IT Manager / COO | March 2025 | 2–3 weeks | Open | Pending completion and auditor sign-off
CA-013 | F-006 | ECC | HIGH | Develop and deliver mandatory security awareness training to all staff | Design training programme covering: phishing recognition, password security, data handling for health data, PDPL obligations (consent, data subject rights, breach reporting), and acceptable use of clinical systems. Deliver to all ~280 staff within 60 days. Record attendance. Schedule annual refresher. | IT Manager / HR | April 2025 | 3–4 weeks | Open | Pending completion and auditor sign-off
CA-014 | F-007 | ECC | HIGH | Establish patch management policy and initiate emergency patching of oldest endpoints | Define patching cadence: critical within 14 days, high within 30 days, standard within 60 days. Immediately prioritise patching of the 41 Windows 10 endpoints on 2021 builds. Validate Napas HIS server patching schedule with Napas vendor. Document patch management procedure. | IT Manager | February 2025 | 2–3 weeks | Open | Pending completion and auditor sign-off
CA-015 | P-002 | PDPL | CRITICAL | Execute PDPL-compliant Data Processing Agreement with Bupa Arabia | Negotiate and execute a DPA with Bupa Arabia covering: data categories shared, purpose limitation (eligibility verification only), security obligations, prohibition on secondary use, breach notification to Rawabi within 24 hours, data retention and deletion schedule, and Rawabi's right to audit. Engage legal counsel. | COO / Legal | April 2025 | 3–4 weeks | Open | Pending completion and auditor sign-off
CA-016 | P-002 | PDPL | CRITICAL | Obtain and execute Nphies data governance framework | Engage MoH / Nphies to obtain the formal data governance framework governing clinical record submission. Document the legal basis (MoH mandate), data elements submitted, Nphies data retention policy, and security responsibilities. Execute any required data sharing agreement or formally record the legal obligation basis. | COO / Legal | April 2025 | 2–3 weeks | Open | Pending completion and auditor sign-off
CA-017 | P-003 | PDPL | HIGH | Develop Personal Data Breach Notification Procedure | Develop breach notification procedure integrated into the IR Plan (CA-012): breach definition and classification, 72-hour SDAIA notification template and contact details, patient notification template, internal escalation path, documentation requirements. Retrospectively assess 2024 IT incidents for PDPL breach implications and document outcomes. | IT Manager / COO | March 2025 | 1–2 weeks | Open | Pending completion and auditor sign-off
CA-018 | P-005 | PDPL | MEDIUM | Draft and publish PDPL-compliant patient privacy notice at all touchpoints | Draft privacy notice disclosing: controller identity, processing purposes, data categories, lawful basis, third-party recipients, retention periods, patient rights, and SDAIA as supervisory authority. Deploy: printed with registration form, displayed at Jeddah and Medina reception, published on organisation website. Coordinate with CA-007 (consent form). | COO / Operations | March 2025 | 1–2 weeks | Open | Pending completion and auditor sign-off
CA-019 | P-002 | PDPL | HIGH | Execute data processing addendum with Al Bilad Lab | Draft and execute a data processing addendum to the laboratory referral agreement covering: categories of patient data shared, purpose limitation, security obligations, breach notification, data retention and disposal, and confidentiality obligations. | COO / Legal | April 2025 | 1–2 weeks | Open | Pending completion and auditor sign-off
PHASE 3 — OPERATIONAL CONTROLS ¦ May – July 2025
CA-020 | F-004 | ECC | CRITICAL | Design and implement network segmentation architecture | Design a segmented network architecture with minimum four zones: Clinical (Napas HIS, Meditech LIS), Imaging (Agfa PACS), Administrative (SAP B1, user endpoints), Management (servers, infrastructure). Implement inter-zone firewall rules on default-deny basis. Produce and maintain network architecture diagram. Phase implementation to avoid clinical service disruption. | IT Manager | July 2025 | 6–8 weeks | Open | Pending completion and auditor sign-off
CA-021 | F-007 | ECC | HIGH | Deploy vulnerability scanning solution and conduct baseline assessment | Select and deploy vulnerability scanning tool (OpenVAS or commercial equivalent). Conduct baseline scan of all endpoints and servers. Produce prioritised remediation list. Establish scanning schedule (monthly for critical systems, quarterly for all assets). Assign remediation owners. | IT Manager | June 2025 | 2–3 weeks | Open | Pending completion and auditor sign-off
CA-022 | F-008 | ECC | MEDIUM | Implement offsite or cloud backup for all critical systems | Implement offsite backup mechanism for Napas HIS, Agfa PACS, and SAP B1 data. Use KSA-region cloud storage to maintain PDPL data residency compliance (e.g., Azure KSA region or equivalent). Establish quarterly restore test schedule. Document RTO and RPO targets for all critical systems. | IT Manager | June 2025 | 2–3 weeks | Open | Pending completion and auditor sign-off
CA-023 | F-003 / F-004 | ECC | HIGH | Renegotiate Napas vendor contract with full security and data protection clauses | Renegotiate the Napas HIS support contract to include: right-to-audit clause, security assessment obligation on Napas, NDA, data protection and PDPL obligations, breach notification within 24 hours, requirement for individual named accounts replacing shared credentials, and access restricted to maintenance window schedules. | COO / Legal | July 2025 | 3–4 weeks | Open | Pending completion and auditor sign-off
CA-024 | P-004 | PDPL | HIGH | Implement data subject rights mechanism — access, correction, deletion, portability | Implement patient rights request intake process: request form (paper and digital), identity verification procedure, defined 30-day response timeframe. Configure Napas HIS workflow for generating patient data access extracts. Document deletion request assessment process (account for mandatory MoH clinical record retention periods). Train reception and admin staff on the process. | IT Manager / Operations | July 2025 | 2–3 weeks | Open | Pending completion and auditor sign-off
CA-025 | — | ECC | MEDIUM | Enable MFA for all privileged and remote access accounts | Enable MFA for all Active Directory privileged accounts, all Microsoft 365 admin accounts, and all remote access connections. Configure Microsoft 365 Conditional Access policies. Assess MFA options for Napas HIS admin access. Deploy Microsoft Authenticator or equivalent for IT staff. | IT Manager | May 2025 | 1–2 weeks | Open | Pending completion and auditor sign-off
CA-026 | — | ECC | MEDIUM | Implement Microsoft 365 data classification and DLP policies | Configure Microsoft 365 sensitivity labels for health data (Sensitive — Health Data, Confidential — Internal). Implement DLP policies restricting external sharing of health data via Teams, SharePoint, and email. Configure audit logging for all admin and user activity. Review and retain logs for 12 months. | IT Manager | June 2025 | 2–3 weeks | Open | Pending completion and auditor sign-off
CA-027 | P-001 | PDPL | MEDIUM | Define data retention schedule aligned with MoH clinical record requirements | Define retention periods for all patient data categories: clinical records (align with MoH minimum retention requirements for Saudi healthcare providers — typically 10 years for adult records), diagnostic imaging, lab results, insurance correspondence, and staff records. Document disposal procedure for records at end of retention. Implement within Napas HIS where technically feasible. | COO / Legal / IT Manager | July 2025 | 1–2 weeks | Open | Pending completion and auditor sign-off
PHASE 4 — SUSTAIN & EMBED ¦ August – October 2025
CA-028 | F-001 | ECC | MEDIUM | Establish quarterly cybersecurity governance review cycle | Schedule and conduct quarterly governance meetings chaired by the cybersecurity lead. Agenda: risk register review, CAP progress, incident review, upcoming audit obligations, and policy updates. Produce meeting minutes as evidence of active governance. First meeting: August 2025. | IT Manager / COO | August 2025 | Ongoing | Open | Pending completion and auditor sign-off
CA-029 | F-006 | ECC | MEDIUM | Introduce phishing simulation programme | Engage a phishing simulation provider or configure Microsoft Defender Attack Simulator. Conduct initial simulation within 90 days of awareness training (CA-013). Report click rates by department. Provide targeted follow-up training for staff who failed the simulation. Schedule quarterly simulations. | IT Manager | September 2025 | 2–3 weeks | Open | Pending completion and auditor sign-off
CA-030 | F-002 | ECC | MEDIUM | Conduct second annual risk assessment cycle | Conduct the second formal risk assessment using the methodology established in CA-011. Review all 25 risks from this report. Identify any new risks arising from remediation activities, system changes, or the evolving threat landscape. Update the risk register and report to governance. | IT Manager | October 2025 | 1–2 weeks | Open | Pending completion and auditor sign-off
CA-031 | P-001 / P-005 | PDPL | LOW | Review and update consent forms and privacy notice for any new processing activities | Conduct an annual review of all PDPL documentation: consent forms, privacy notice, data processing register, and DPAs. Update to reflect any new processing activities, new third-party relationships, or changes in SDAIA regulatory guidance. Obtain legal review of any material changes. | COO / Legal | October 2025 | 1 week | Open | Pending completion and auditor sign-off
CA-032 | P-003 | PDPL | LOW | Conduct PDPL compliance monitoring review and staff refresher training | Review PDPL compliance status against all obligations. Assess any new SDAIA guidance or enforcement decisions published since January 2025. Deliver PDPL refresher training to all staff, with particular focus on data subject rights requests and breach reporting. Document training attendance. | IT Manager / COO | October 2025 | 1–2 weeks | Open | Pending completion and auditor sign-off

## Gantt_Chart
Corrective Action Plan — Gantt Chart ¦ Rawabi Health Services Co. ¦ RCA-P4-006
December 2024 – October 2025 · 32 Actions across 4 Phases · CONFIDENTIAL
ID | Corrective Action | Priority | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025 | Jul 2025 | Aug 2025 | Sep 2025 | Oct 2025
PHASE 1 — CRITICAL CONTAINMENT ¦ December 2024 – January 2025
CA-001 | Rotate Napas HIS shared administrative credential immed… | CRIT
CA-002 | Implement dedicated VPN tunnel or jump server for all N… | CRIT
CA-003 | Enable session logging and recording for all Napas vend… | CRIT
CA-004 | Issue data protection addendum to Napas vendor support … | CRIT
CA-005 | Include Agfa PACS DICOM imaging data in backup schedule… | HIGH
CA-006 | Conduct documented restore test for Napas HIS backup da… | HIGH
CA-007 | Design and implement PDPL-compliant patient consent for… | CRIT
CA-008 | Map all data processing activities to PDPL lawful bases | CRIT
PHASE 2 — GOVERNANCE BUILD ¦ February – April 2025
CA-009 | Appoint cybersecurity lead with defined authority and a… | CRIT
CA-010 | Draft and obtain executive approval for Information Sec… | CRIT
CA-011 | Conduct cybersecurity risk assessment and establish ris… | CRIT
CA-012 | Develop and approve Cybersecurity Incident Response Pla… | HIGH
CA-013 | Develop and deliver mandatory security awareness traini… | HIGH
CA-014 | Establish patch management policy and initiate emergenc… | HIGH
CA-015 | Execute PDPL-compliant Data Processing Agreement with B… | CRIT
CA-016 | Obtain and execute Nphies data governance framework | CRIT
CA-017 | Develop Personal Data Breach Notification Procedure | HIGH
CA-018 | Draft and publish PDPL-compliant patient privacy notice… | MEDI
CA-019 | Execute data processing addendum with Al Bilad Lab | HIGH
PHASE 3 — OPERATIONAL CONTROLS ¦ May – July 2025
CA-020 | Design and implement network segmentation architecture | CRIT
CA-021 | Deploy vulnerability scanning solution and conduct base… | HIGH
CA-022 | Implement offsite or cloud backup for all critical syst… | MEDI
CA-023 | Renegotiate Napas vendor contract with full security an… | HIGH
CA-024 | Implement data subject rights mechanism — access, corre… | HIGH
CA-025 | Enable MFA for all privileged and remote access account… | MEDI
CA-026 | Implement Microsoft 365 data classification and DLP pol… | MEDI
CA-027 | Define data retention schedule aligned with MoH clinica… | MEDI
PHASE 4 — SUSTAIN & EMBED ¦ August – October 2025
CA-028 | Establish quarterly cybersecurity governance review cyc… | MEDI
CA-029 | Introduce phishing simulation programme | MEDI
CA-030 | Conduct second annual risk assessment cycle | MEDI
CA-031 | Review and update consent forms and privacy notice for … | LOW
CA-032 | Conduct PDPL compliance monitoring review and staff ref… | LOW
Legend
██ | Phase 1 — Critical Containment
██ | Phase 2 — Governance Build
██ | Phase 3 — Operational Controls
██ | Phase 4 — Sustain & Embed

## Finding_Crosswalk
Finding-to-Action Crosswalk ¦ Rawabi Health Services Co. ¦ RCA-P4-006
Maps every audit finding (ECC and PDPL) to its corrective action(s) · CONFIDENTIAL
Finding ID | Finding Title | Severity | Corrective Action(s) | Phase | Target
F-001 | No cybersecurity strategy or governance framework | CRITICAL | CA-009, CA-010, CA-028 | Phase 1–2 | Mar 2025
F-002 | No cybersecurity risk assessment process | CRITICAL | CA-011, CA-030 | Phase 2, 4 | Mar / Oct 2025
F-003 | Napas vendor remote access uncontrolled — LIVE RISK | CRITICAL | CA-001, CA-002, CA-003, CA-004, CA-023 | Phase 1, 3 | Jan / Jul 2025
F-004 | No network segmentation — flat network | CRITICAL | CA-020 | Phase 3 | Jul 2025
F-005 | No cybersecurity incident response procedure | HIGH | CA-012 | Phase 2 | Mar 2025
F-006 | No security awareness training programme | HIGH | CA-013, CA-029 | Phase 2, 4 | Apr / Sep 2025
F-007 | Vulnerability management absent — no patching schedule | HIGH | CA-014, CA-021 | Phase 2, 3 | Feb / Jun 2025
F-008 | No backup integrity testing or offsite recovery | MEDIUM | CA-005, CA-006, CA-022 | Phase 1, 3 | Jan / Jun 2025
P-001 | No lawful basis documented; consent mechanism absent | CRITICAL | CA-007, CA-008, CA-027, CA-031 | Phase 1, 3, 4 | Jan / Jul / Oct 2025
P-002 | No Data Processing Agreements — Bupa Arabia and Nphies | CRITICAL | CA-004, CA-015, CA-016, CA-019 | Phase 1–3 | Apr 2025
P-003 | No breach notification procedure — 72-hour SDAIA obligation | HIGH | CA-012, CA-017, CA-032 | Phase 2, 4 | Mar / Oct 2025
P-004 | No data subject rights mechanism | HIGH | CA-024 | Phase 3 | Jul 2025
P-005 | Privacy notice non-compliant | MEDIUM | CA-018, CA-031 | Phase 2, 4 | Mar / Oct 2025