## Cover
RESOLUTE COMPLIANCE ADVISORY LLP
Governance · Risk · Compliance
REMEDIATION ROADMAP
ISO 27001:2022 / GDPR / DPDP Act 2023 · Medlink India Pvt. Ltd.
Document Ref | RCA-P2-007
Client | Medlink India Pvt. Ltd.
Prepared by | kay Shahbaaz, GRC Analyst
Programme Period | July 2024 – June 2025
Report Date | 15 June 2024
Version | v1.0
Classification | CONFIDENTIAL
Total Actions | 34 remediation actions across 4 phases
Frameworks | ISO 27001:2022 + UK GDPR + DPDP Act 2023
Cert. Target | ISO 27001:2022 Stage 1 audit readiness: Q2 2025 (10–14 months)
PHASE OVERVIEW
Phase 1 — Immediate & Short-Term | July – August 2024 ¦ 10 actions ¦ Critical & High findings; live risks
Phase 2 — Governance & Privacy Foundations | September – November 2024 ¦ 7 actions ¦ Governance, privacy, and vendor management
Phase 3 — Controls Implementation | December 2024 – February 2025 ¦ 7 actions ¦ Technical controls, logging, training
Phase 4 — Assurance & Continuous Improvement | March – June 2025 ¦ 10 actions ¦ Assurance, certification readiness, ongoing
ACTION SEVERITY (based on linked finding/risk)
Critical — foundational control failure; immediate or near-immediate action required
High — significant gap; structured remediation within 90 days
Medium — control deficiency; address within programme timeline

## Dashboard
REMEDIATION ROADMAP DASHBOARD · Medlink India Pvt. Ltd. · RCA-P2-007 · CONFIDENTIAL
REMEDIATION ACTIONS BY PHASE
| Phase 1 Jul–Aug 2024 |  | Phase 2 Sep–Nov 2024 |  | Phase 3 Dec 24–Feb 25 | TOTAL | Phase 4 Mar–Jun 2025
| 10 |  | 7 |  | 7 | 34 | 10
PHASE DETAIL
| Phase | Period | Actions | Critical | High | Med
| Phase 1 — Immediate & Short-Term | Jul – Aug 2024 | 10 | 6 | 2 | 2
| Phase 2 — Governance & Privacy Foundations | Sep – Nov 2024 | 7 | 3 | 3 | 1
| Phase 3 — Controls Implementation | Dec 2024 – Feb 2025 | 7 | 1 | 3 | 3
| Phase 4 — Assurance & Continuous Improvement | Mar – Jun 2025 | 10 | 2 | 3 | 5
| TOTAL | Jul 2024 – Jun 2025 | 34 | 12 | 11 | 11
FRAMEWORK COVERAGE
| ISO 27001:2022 | 24 actions | RA-001, RA-002, RA-003, RA-004, RA-005, RA-010, RA-011, RA-014 ... (+16 more)
| UK GDPR | 12 actions | RA-004, RA-006, RA-008, RA-009, RA-012, RA-014, RA-015, RA-016 ... (+4 more)
| DPDP Act 2023 | 10 actions | RA-004, RA-007, RA-009, RA-013, RA-014, RA-015, RA-016, RA-019 ... (+2 more)
| All Frameworks | 2 actions | RA-001, RA-002

## Remediation Roadmap
REMEDIATION ROADMAP · Medlink India Pvt. Ltd. · RCA-P2-007 · CONFIDENTIAL · 15 June 2024
Action ID | Phase | Category | Remediation Action | Finding Refs | Risk Refs | Severity | Owner | Start Date | End Date | Effort | Framework | Success Criteria
Phase 1 — Immediate & Short-Term
RA-001 | Phase 1 | Secrets Management | IMMEDIATE: Rotate AWS IAM access key pair exposed in GitHub repository. Generate new key pair, update all dependent services and CI/CD pipelines, deactivate and delete the old key. Review CloudTrail logs for the past 90 days for evidence of unauthorised usage. | F-002 | R-004 | Critical | Head of Engineering | 01 Jul 2024 | 03 Jul 2024 | 1 day | ISO 27001 / All | Old AWS IAM key deactivated and deleted; new key active; CloudTrail review completed and documented; no evidence of unauthorised usage confirmed or incident response initiated.
RA-002 | Phase 1 | Secrets Management | IMMEDIATE: Regenerate Twilio API token exposed in GitHub repository. Update application configuration with new token. Verify SMS delivery functionality post-rotation. | F-002 | R-005 | Critical | Head of Engineering | 01 Jul 2024 | 03 Jul 2024 | 0.5 days | ISO 27001 / All | Old Twilio token revoked; new token active; patient SMS delivery confirmed operational.
RA-003 | Phase 1 | Secrets Management | Implement AWS Secrets Manager for all production credentials (AWS keys, Twilio token, database credentials, third-party API keys). Configure automatic rotation for all secrets with rotation periods appropriate to credential sensitivity (AWS keys: 90 days; API tokens: 180 days). Remove all hardcoded credentials from both identified repositories and conduct a full repository scan across the GitHub organisation. | F-002 | R-004 / R-005 / R-006 | Critical | Head of Engineering | 04 Jul 2024 | 31 Jul 2024 | 3 weeks | ISO 27001 — A.8.25 / A.8.28 | All production credentials stored in AWS Secrets Manager; automatic rotation configured; zero hardcoded credentials confirmed via full GitHub organisation scan; CI/CD pipelines updated to retrieve secrets from Secrets Manager.
RA-004 | Phase 1 | Encryption | Apply S3 bucket policy to all 31 Medlink S3 buckets denying s3:PutObject without server-side encryption (aws:kms). Prioritise the 7 buckets confirmed to contain unencrypted patient diagnostic attachments. Deploy via AWS Config rule to enforce continuously. Run S3 Batch Operations job to retroactively encrypt existing unencrypted objects. | F-004 | R-007 | Critical | IT Operations / AWS Admin | 01 Jul 2024 | 31 Jul 2024 | 2 weeks | ISO 27001 — A.8.24 / UK GDPR Art. 32 / DPDP Act S.8(4) | All 31 S3 buckets have SSE-KMS enforcement confirmed via AWS Config compliance report; S3 Batch Operations encryption job completed with zero errors; AWS Config rule shows 100% compliant.
RA-005 | Phase 1 | IS Policy & Governance | Update the draft Information Security Policy to reference ISO 27001:2022 (replacing ISO 27001:2013 throughout), reflect Medlink's current operational context (AWS/Azure AD environment, healthtech data classification, GDPR/DPDP dual regulatory scope), and include all required elements per Clause 5.2. Obtain formal approval from the Board or equivalent executive authority. Communicate to all staff. | F-001 | R-001 | Critical | CTO / Board | 01 Jul 2024 | 15 Aug 2024 | 6 weeks | ISO 27001 — A.5.1 / Clause 5.2 | IS policy approved and signed by Board/CEO; communicated to all staff via all-hands and email; embedded in employee onboarding pack; annual review scheduled with named owner.
RA-006 | Phase 1 | Privacy — DPO & Governance | Appoint a Data Protection Officer (DPO) with the independence, expertise, and resources required by Articles 37–39 UK GDPR. The DPO must not hold operational responsibilities creating a conflict of interest (i.e. not the CTO). Options: appoint a senior legal/compliance professional or engage a DPO-as-a-Service provider. Register the DPO with the ICO and publish contact details. | G-003 | R-002 | High | Board / CTO | 01 Jul 2024 | 30 Jul 2024 | 4 weeks | UK GDPR — Article 37 | DPO formally appointed with documented mandate; DPO registered with ICO (registration confirmation obtained); DPO contact details published on Medlink website and in UK-facing privacy notice.
RA-007 | Phase 1 | Privacy — DPDP Act | Appoint a named Grievance Officer under DPDP Act Section 13(3). The role may be held concurrently with the DPO function (RA-006) if the appointee has appropriate expertise in both frameworks. Publish the Grievance Officer's name and contact email in the Medlink privacy notice and within the patient-facing mobile application. | D-004 | R-003 / R-020 | Medium | Board / CTO | 01 Jul 2024 | 30 Jul 2024 | 1 week | DPDP Act 2023 — Section 13(3) | Grievance Officer named and appointed; contact details published in privacy notice and in-app; internal procedure for receiving and responding to grievances documented.
RA-008 | Phase 1 | Vendor Management | Initiate Article 28 UK GDPR Data Processing Agreement negotiations with all three UK clinic clients. Use a standard DPA template covering all mandatory Article 28(3) provisions: processing instructions, confidentiality, security measures, sub-processor management, data subject rights assistance, deletion/return of data, and audit cooperation rights. | G-001 | R-002 / R-013 | Critical | Legal / CTO | 01 Jul 2024 | 31 Aug 2024 | 6 weeks | UK GDPR — Article 28 | Executed DPAs in place with all three UK clinic clients; DPA template approved by legal counsel; DPA execution included as precondition in new UK client onboarding process.
RA-009 | Phase 1 | Incident Response | Resolve outstanding January 2024 erasure request from Indian patient. Confirm whether a legal basis exists for continued retention of the patient's data; if not, initiate deletion. Document the outcome and communicate formally to the requester. | D-003 | R-020 | High | Legal / Engineering | 01 Jul 2024 | 15 Jul 2024 | 2 weeks | DPDP Act — Sections 11–13 / UK GDPR Art. 5(1)(e) | January 2024 erasure request formally resolved; outcome documented; requester notified in writing; response process documented as basis for the rights fulfilment procedure (RA-019).
RA-010 | Phase 1 | Encryption — Key Management | Enable automatic annual key rotation on all three AWS KMS Customer Managed Keys (CMKs). Document the CMK inventory including key ID, creation date, usage (which buckets/resources), and rotation schedule. Assign a named key custodian. | F-011 | R-008 | Medium | IT Operations | 01 Jul 2024 | 15 Jul 2024 | 1 week | ISO 27001 — A.8.24 | Automatic rotation enabled on all three CMKs; rotation confirmation in AWS KMS console; CMK inventory documented with custodian assigned; cryptographic key management policy drafted.
Phase 2 — Governance & Privacy Foundations
RA-011 | Phase 2 | Risk Assessment | Define and document a formal IS risk assessment methodology covering: risk identification process linked to the asset register; Likelihood x Impact scoring matrix (1–5) with rating bands; risk register template; risk treatment options and decision criteria; and risk acceptance criteria. Conduct the initial formal risk assessment as a facilitated workshop with CTO, Head of Engineering, and IT Operations Lead. Produce the approved risk register (basis: RCA-P2-006). | F-003 | R-001 | Critical | CTO | 01 Sep 2024 | 30 Sep 2024 | 4 weeks | ISO 27001 — Clause 6.1.2 | Risk assessment methodology documented and approved; initial risk register produced, reviewed, and signed off by CTO; annual review cycle scheduled; risk register owner assigned.
RA-012 | Phase 2 | Privacy — DPIA | Conduct a Data Protection Impact Assessment (DPIA) for Medlink's core processing activity: large-scale processing of special category health data. DPIA must cover: description of processing (purpose, necessity, proportionality); assessment of risks to data subjects; cross-reference to ISO findings affecting UK patient data (F-004, F-006, F-012); proposed measures to address identified risks; residual risk assessment. DPO to oversee. Consult ICO if residual risk remains high. | G-002 | R-002 | Critical | DPO / CTO | 01 Sep 2024 | 31 Oct 2024 | 8 weeks | UK GDPR — Article 35 | DPIA completed, documented, and approved by DPO; risks and mitigating measures recorded; DPIA reviewed and updated annually and upon any significant change to processing; ICO consultation record maintained if applicable.
RA-013 | Phase 2 | Privacy — Consent Redesign | Redesign the patient consent mechanism in the Medlink mobile application and web portal to comply with DPDP Act Section 6. Implement a layered consent notice presented before data collection listing each distinct processing purpose. Implement separate consent toggles per purpose. Build consent withdrawal mechanism (in-app and web). Record consent by purpose with timestamp and version. Present updated consent notice to existing patients at next login. | D-001 | R-003 / R-019 | Critical | Engineering / Legal | 01 Sep 2024 | 31 Oct 2024 | 8 weeks | DPDP Act — Section 6 | New consent mechanism live in production; consent notice reviewed by legal counsel; consent records stored with timestamp and version; withdrawal mechanism functional and tested; existing patient re-consent completed within 60 days of go-live.
RA-014 | Phase 2 | Incident Response | Develop a documented Information Security Incident Response Procedure covering: incident definition and classification criteria; internal escalation matrix; regulatory notification obligations with jurisdiction determination step (ICO for UK GDPR — 72 hours; DPB for DPDP Act); data subject notification procedure and templates; client notification procedure; post-incident review process. Assign IR Lead. Conduct tabletop exercise within 30 days of procedure approval. | F-006 / D-002 | R-016 / R-017 / R-018 | High | CTO / Legal | 01 Sep 2024 | 31 Oct 2024 | 8 weeks | ISO 27001 — A.5.24–A.5.26 / UK GDPR Art. 33 / DPDP Act S.8(6) | IR procedure approved and communicated; ICO notification template prepared; DPB notification template prepared; IR Lead assigned; tabletop exercise completed with findings documented.
RA-015 | Phase 2 | Vendor Management | Conduct security assessments of all seven lab integration partners: issue security questionnaire covering IS controls, certification status (ISO 27001 / SOC 2), breach notification procedures, and sub-processor arrangements. Execute data processing agreements and/or contractual security clauses with each partner. For UK patient data flows: Article 28 DPAs required. For Indian patient data: DPDP Act Section 8(5) processor obligations to be documented. | F-005 | R-012 / R-013 / R-030 | High | Legal / CTO / Procurement | 01 Sep 2024 | 30 Nov 2024 | 12 weeks | ISO 27001 — A.5.19 / A.5.20 / UK GDPR Art. 28 / DPDP Act S.8(5) | Security questionnaire completed and reviewed for all 7 lab partners; DPAs or processor clauses executed with all partners; high-risk partners identified for annual review; vendor security assessment framework documented as a reusable process.
RA-016 | Phase 2 | Privacy — Retained Data | Assess the legal basis for continued retention of patient data belonging to two terminated clinic clients. If no lawful basis exists for retention, initiate secure deletion or archival in consultation with the former clients. Draft data retention schedule covering all data categories and reconciling MCI minimum retention floors with GDPR/DPDP maximum ceilings. | G-004 | R-021 | High | Legal / Engineering | 01 Sep 2024 | 31 Oct 2024 | 8 weeks | UK GDPR — Art. 5(1)(e) / DPDP Act S.8(7) / MCI Guidelines | Legal basis assessment for retained client data documented; deletion or archival initiated where no lawful basis found; data retention schedule drafted covering all data categories with jurisdiction-specific retention periods.
RA-017 | Phase 2 | Privacy — Privacy Notice | Rewrite the Medlink privacy notice(s) to be UK GDPR-compliant: include all mandatory Articles 13/14 elements (DPO contact, Article 9(2) condition, special category data categories, ICO complaint right, transfer safeguards, retention periods, all data subject rights). Create separate patient-facing and website/marketing privacy notices. Publish and date-stamp. | G-005 | R-002 | Medium | Legal / Marketing | 01 Oct 2024 | 31 Oct 2024 | 4 weeks | UK GDPR — Articles 13 / 14 | Updated privacy notice published on website and in mobile app; notice reviewed by legal counsel; separate patient and marketing notices live; notice version and date recorded; annual review scheduled.
Phase 3 — Controls Implementation
RA-018 | Phase 3 | Logging & Monitoring | Implement application-level audit logging in the Medlink EMR platform to capture: user ID, session token, timestamp, action type (view/create/update/delete), and patient record ID for every data access event. Enable RDS PostgreSQL query logging (log_statement: 'ddl' minimum, 'all' for PHI tables). Implement centralised log aggregation (AWS CloudWatch Logs). Define and implement log retention policy (12 months online, 3 years archived). Protect logs against tampering. | F-012 | R-010 / R-025 | Medium | Head of Engineering | 01 Dec 2024 | 28 Feb 2025 | 12 weeks | ISO 27001 — A.8.15 / UK GDPR Art. 5(2) | Application audit log operational in production; all PHI access events logged with required fields; RDS query logging enabled; CloudWatch log groups configured with appropriate retention and access controls; log integrity validation enabled; sample log review confirms completeness.
RA-019 | Phase 3 | Privacy — Data Principal Rights | Implement a Data Principal rights management process and mechanism: dedicated rights request portal (web and in-app); internal procedure for receiving, logging, assessing, and responding to requests within 30 days; fulfilment workflows for access, correction, and erasure requests in the EMR database; ensure selective erasure does not compromise integrity of other patients' records. Assign the Grievance Officer (RA-007) as point of contact. | D-003 | R-020 | High | Engineering / Legal | 01 Dec 2024 | 31 Jan 2025 | 8 weeks | DPDP Act — Sections 11–13 / UK GDPR Arts. 15–17 | Rights request portal live and tested; internal procedure documented and communicated to relevant staff; end-to-end fulfilment tested for access, correction, and erasure request types; response timeline tracking implemented; Grievance Officer named as contact.
RA-020 | Phase 3 | Secrets Management — CI/CD | Implement secrets scanning as a mandatory pre-merge gate in the GitHub Actions CI/CD pipeline (using GitHub Advanced Security secret scanning or equivalent — e.g. TruffleHog, GitGuardian). Configure pipeline to block merges where secrets are detected. Enable GitHub secret scanning across all repositories in the organisation. Document and publish a secure coding standard explicitly prohibiting hardcoded secrets. | F-002 | R-006 | Critical | Head of Engineering | 01 Dec 2024 | 31 Dec 2024 | 4 weeks | ISO 27001 — A.8.25 / A.8.29 | Secrets scanning gate active in CI/CD pipeline; merge blocked on secrets detection confirmed by test commit; GitHub secret scanning enabled across all repositories; secure coding standard published and accessible to all engineers.
RA-021 | Phase 3 | Data Classification — Operational Enforcement | Operationalise the data classification scheme: implement S3 object tagging for classification (aws:classification tag enforced via bucket policy); define explicit handling requirements for each tier including where to store, how to transmit, encryption requirements, retention, and disposal; establish labelling requirement for internal documents and emails containing Restricted or Confidential data; review classification assignments for all primary data stores. | F-010 | R-009 | Medium | CTO / IT Operations | 01 Dec 2024 | 31 Jan 2025 | 8 weeks | ISO 27001 — A.5.12 / A.5.13 | S3 object tagging implemented and enforced; handling requirements matrix published for each classification tier; data store classification review completed and documented; classification labelling included in updated security awareness training (RA-023).
RA-022 | Phase 3 | Cryptographic Policy | Document a cryptographic key management policy covering: key generation standards (AWS KMS, minimum 256-bit AES); rotation schedule (annual minimum); key access controls (least privilege IAM policies restricting key usage to specific roles and services); key deletion procedure (7-day minimum waiting period, dual approval). Eliminate use of production PHI in test environments — implement data masking or synthetic patient data generation for test use. | F-011 | R-008 / R-009 | Medium | IT Operations / Head of Engineering | 01 Dec 2024 | 31 Jan 2025 | 8 weeks | ISO 27001 — A.8.24 / A.8.33 | Cryptographic key management policy approved; IAM key usage policies updated to least privilege; test environment PHI eliminated — synthetic data or masked data confirmed in use; production data copy policy prohibited in documented SDLC policy.
RA-023 | Phase 3 | Security Awareness Training | Design and implement a tiered annual security awareness training programme: (1) All-staff programme covering data classification, patient data handling obligations under GDPR and DPDP Act, phishing awareness, incident reporting, and the updated IS policy; (2) Engineering-specific programme covering OWASP API Security Top 10, secrets management, secure coding standards, and secure SDLC. Conduct quarterly phishing simulation exercises. Track completion rates by department. Set minimum 95% completion target. | F-007 | R-028 | High | CTO / HR | 01 Jan 2025 | 28 Feb 2025 | 8 weeks | ISO 27001 — A.6.3 | Training programme delivered to 100% of staff (target: 95% minimum completion); engineering training completed by all 60 engineers; phishing simulation baseline established; completion rates recorded by department; annual schedule confirmed for subsequent years.
RA-024 | Phase 3 | Physical Security | Implement visitor log at Mumbai office reception: visitor name, organisation, purpose, host employee, entry and exit time, signature. Brief reception staff on procedure. Install CCTV coverage inside the server room with footage retained for minimum 90 days. Restrict CCTV footage access to authorised IT management. Confirm backup tape encryption status and implement if not present. | F-008 | R-022 / R-023 | High | IT Operations / Facilities | 01 Dec 2024 | 31 Dec 2024 | 4 weeks | ISO 27001 — A.7.2 / A.7.4 | Visitor log in operation at reception; CCTV installed in server room with confirmed retention of 90 days; backup tape encryption confirmed; CCTV access restricted to named IT management; physical security monitoring policy documented.
Phase 4 — Assurance & Continuous Improvement
RA-025 | Phase 4 | Personnel Security | Implement mandatory background screening policy for all new hires accessing Restricted or Confidential data. Screening to include: identity verification, 3-year employment history verification, and criminal record check (where legally permissible). Initiate retrospective screening programme for the 34 directly hired engineers without background checks on file. Embed requirement in HR onboarding process and employment contracts. | F-009 | R-027 | High | HR / CTO | 01 Mar 2025 | 30 Apr 2025 | 8 weeks | ISO 27001 — A.6.1 | Background screening policy approved and embedded in HR process; retrospective programme initiated for all 34 engineers; refusals escalated to CTO; 100% of new PHI-access hires screened before system access granted.
RA-026 | Phase 4 | Application Security | Implement certificate pinning in both Android and iOS Medlink mobile applications (public key pinning to issuing CA recommended). Close the outstanding January 2024 VAPT finding MP-07. Establish a VAPT finding remediation tracking process: all findings assigned owners and target dates; sign-off process upon closure; overdue findings escalated to CTO. | F-013 | R-024 | Medium | Head of Engineering | 01 Mar 2025 | 31 Mar 2025 | 4 weeks | ISO 27001 — A.8.26 / A.8.8 | Certificate pinning implemented and verified in both Android and iOS apps; VAPT finding MP-07 formally closed; VAPT finding tracker operational with all outstanding findings logged; no findings open beyond their target remediation date.
RA-027 | Phase 4 | Vendor Management | Assess Razorpay's security posture: obtain PCI-DSS attestation of compliance (AoC); review Razorpay's GDPR/DPDP-compliant DPA; confirm sub-processor arrangements. Conduct security assessment of Twilio and AWS SES for completeness of vendor security programme. Establish annual vendor review cycle for all assessed vendors. | F-005 | R-014 / R-015 | High | Finance / Legal / Procurement | 01 Mar 2025 | 30 Apr 2025 | 8 weeks | ISO 27001 — A.5.19 / A.5.20 / A.5.22 | Razorpay PCI-DSS AoC obtained and filed; Razorpay, Twilio, and AWS SES DPAs reviewed and confirmed compliant; annual vendor review calendar established for all key suppliers.
RA-028 | Phase 4 | IS Governance — ISMS Internal Audit | Conduct the first formal ISMS internal audit against ISO 27001:2022, covering: compliance with the approved IS policy (RA-005); implementation of risk treatment actions (RA-011); effectiveness of controls deployed in Phases 1–3; residual non-conformities. Produce internal audit report. Present findings to senior management. Schedule Stage 1 certification audit with an accredited certification body. | F-001 / F-003 | R-001 | Critical | CTO / External Auditor | 01 Apr 2025 | 30 Apr 2025 | 4 weeks | ISO 27001 — Clause 9.2 | ISMS internal audit completed with documented findings report; senior management review conducted (Clause 9.3 management review); residual non-conformities identified and assigned to corrective actions; Stage 1 certification audit scheduled with accredited body.
RA-029 | Phase 4 | Retention Schedule — Implementation | Implement the data retention schedule developed in RA-016: configure S3 lifecycle policies for automated archival and deletion; implement database record archival process for records beyond the active retention period; configure automated deletion triggers for data at end of retention period. Test deletion process on non-production environment before production deployment. | G-004 | R-021 | High | Engineering / Legal | 01 Mar 2025 | 30 Apr 2025 | 8 weeks | UK GDPR — Art. 5(1)(e) / DPDP Act S.8(7) / ISO 27001 — A.8.10 | S3 lifecycle policies configured and verified for all data categories; automated deletion confirmed operational in test environment; production deployment completed; retention schedule compliance report available from AWS Config; no terminated-client data retained beyond schedule.
RA-030 | Phase 4 | DPDP Act — Rules Monitoring | Monitor MeitY notification of DPDP Act implementing rules. Upon rules notification: review all existing procedures (incident response, consent, rights mechanism, Grievance Officer response timelines) against the prescribed requirements; update procedures to reflect any new obligations; ensure breach notification procedure reflects the prescribed timelines for DPB notification and Data Principal notification. | D-002 | R-031 | Medium | Legal / Compliance | 01 Mar 2025 | 30 Jun 2025 | Ongoing | DPDP Act 2023 — All | DPDP implementing rules monitored; upon notification, all affected procedures updated within 60 days; updated procedures reviewed by legal counsel; staff notified of changes.
RA-031 | Phase 4 | Access Control — Recertification | Establish a semi-annual access recertification programme: review all user access roles in the EMR application and AWS IAM against current job roles; revoke access that is no longer required; document the review and approval process. Implement privileged access management (PAM) controls for production system administrators. | A.5.18 | R-010 / R-011 | Medium | IT Operations / CTO | 01 Mar 2025 | 30 Apr 2025 | 4 weeks | ISO 27001 — A.5.18 / A.8.2 | First access recertification completed with documented findings; stale access revoked; semi-annual schedule established; PAM controls defined and implementation roadmap agreed.
RA-032 | Phase 4 | Business Continuity | Document an ICT Continuity Plan defining Recovery Time Objective (RTO) and Recovery Point Objective (RPO) for the Medlink platform; conduct annual backup restoration test (RDS and S3); define escalation procedure for extended outages and client notification process. Test plan in a tabletop exercise. | A.5.30 | R-029 | Medium | CTO / IT Operations | 01 May 2025 | 30 Jun 2025 | 8 weeks | ISO 27001 — A.5.29 / A.5.30 | ICT Continuity Plan approved; RTO/RPO targets defined and agreed with senior management; backup restoration test completed successfully and documented; tabletop exercise completed.
RA-033 | Phase 4 | Threat Intelligence & Monitoring | Subscribe to a healthcare sector threat intelligence feed (e.g. Health-ISAC, CERT-In advisories). Implement AWS Security Hub and Amazon GuardDuty for continuous threat detection across the AWS environment. Define alert triage process and escalation to IT Operations / CTO. | A.5.7 | R-001 | Medium | IT Operations / CTO | 01 May 2025 | 30 Jun 2025 | 8 weeks | ISO 27001 — A.5.7 / A.8.16 | CERT-In and sector threat feed subscription active; GuardDuty and Security Hub enabled in both AWS Mumbai and AWS London accounts; alert triage SOP documented; first monthly threat intelligence review meeting held.
RA-034 | Phase 4 | Certification Readiness | Following the ISMS internal audit (RA-028), address all residual non-conformities identified. Prepare the ISMS documentation package for Stage 1 audit: IS policy, SoA (RCA-P2-005 updated), risk register (RCA-P2-006 updated), internal audit report, management review minutes. Engage accredited certification body for Stage 1 audit scheduling. | All | All | Critical | CTO / ISMS Owner | 01 May 2025 | 30 Jun 2025 | 8 weeks | ISO 27001:2022 — Full Standard | All residual non-conformities from internal audit addressed; ISMS documentation package complete and reviewed; Stage 1 audit scheduled and confirmed with accredited certification body; management sign-off on certification readiness obtained.

## Gantt Chart
REMEDIATION ROADMAP — GANTT CHART · Medlink India Pvt. Ltd. · RCA-P2-007 · Jul 2024 – Jun 2025
ID | Action | Owner | Sev. | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025 | Mar 2025 | Apr 2025 | May 2025 | Jun 2025
Phase 1 — Immediate & Short-Term
RA-001 | Secrets Management: IMMEDIATE: Rotate AWS IAM access key pair exposed in Gi... | Head of Engineering | Crit | ▶
RA-002 | Secrets Management: IMMEDIATE: Regenerate Twilio API token exposed in GitHu... | Head of Engineering | Crit | ▶
RA-003 | Secrets Management: Implement AWS Secrets Manager for all production creden... | Head of Engineering | Crit | ▶
RA-004 | Encryption: Apply S3 bucket policy to all 31 Medlink S3 buckets den... | IT Operations / AWS Admin | Crit | ▶
RA-005 | IS Policy & Governance: Update the draft Information Security Policy to referen... | CTO / Board | Crit | ▶ | ◀
RA-006 | Privacy — DPO & Governance: Appoint a Data Protection Officer (DPO) with the indepe... | Board / CTO | High | ▶
RA-007 | Privacy — DPDP Act: Appoint a named Grievance Officer under DPDP Act Sectio... | Board / CTO | Medi | ▶
RA-008 | Vendor Management: Initiate Article 28 UK GDPR Data Processing Agreement n... | Legal / CTO | Crit | ▶ | ◀
RA-009 | Incident Response: Resolve outstanding January 2024 erasure request from I... | Legal / Engineering | High | ▶
RA-010 | Encryption — Key Management: Enable automatic annual key rotation on all three AWS K... | IT Operations | Medi | ▶
Phase 2 — Governance & Privacy Foundations
RA-011 | Risk Assessment: Define and document a formal IS risk assessment methodo... | CTO | Crit |  |  | ▶
RA-012 | Privacy — DPIA: Conduct a Data Protection Impact Assessment (DPIA) for ... | DPO / CTO | Crit |  |  | ▶ | ◀
RA-013 | Privacy — Consent Redesign: Redesign the patient consent mechanism in the Medlink m... | Engineering / Legal | Crit |  |  | ▶ | ◀
RA-014 | Incident Response: Develop a documented Information Security Incident Resp... | CTO / Legal | High |  |  | ▶ | ◀
RA-015 | Vendor Management: Conduct security assessments of all seven lab integrati... | Legal / CTO / Procurement | High |  |  | ▶ | █ | ◀
RA-016 | Privacy — Retained Data: Assess the legal basis for continued retention of patie... | Legal / Engineering | High |  |  | ▶ | ◀
RA-017 | Privacy — Privacy Notice: Rewrite the Medlink privacy notice(s) to be UK GDPR-com... | Legal / Marketing | Medi |  |  |  | ▶
Phase 3 — Controls Implementation
RA-018 | Logging & Monitoring: Implement application-level audit logging in the Medlin... | Head of Engineering | Medi | [5 empty] | ▶ | █ | ◀
RA-019 | Privacy — Data Principal Rights: Implement a Data Principal rights management process an... | Engineering / Legal | High | [5 empty] | ▶ | ◀
RA-020 | Secrets Management — CI/CD: Implement secrets scanning as a mandatory pre-merge gat... | Head of Engineering | Crit | [5 empty] | ▶
RA-021 | Data Classification — Operational Enforcement: Operationalise the data classification scheme: implemen... | CTO / IT Operations | Medi | [5 empty] | ▶ | ◀
RA-022 | Cryptographic Policy: Document a cryptographic key management policy covering... | IT Operations / Head of Engineering | Medi | [5 empty] | ▶ | ◀
RA-023 | Security Awareness Training: Design and implement a tiered annual security awareness... | CTO / HR | High | [6 empty] | ▶ | ◀
RA-024 | Physical Security: Implement visitor log at Mumbai office reception: visit... | IT Operations / Facilities | High | [5 empty] | ▶
Phase 4 — Assurance & Continuous Improvement
RA-025 | Personnel Security: Implement mandatory background screening policy for all... | HR / CTO | High | [8 empty] | ▶ | ◀
RA-026 | Application Security: Implement certificate pinning in both Android and iOS M... | Head of Engineering | Medi | [8 empty] | ▶
RA-027 | Vendor Management: Assess Razorpay's security posture: obtain PCI-DSS atte... | Finance / Legal / Procurement | High | [8 empty] | ▶ | ◀
RA-028 | IS Governance — ISMS Internal Audit: Conduct the first formal ISMS internal audit against IS... | CTO / External Auditor | Crit | [9 empty] | ▶
RA-029 | Retention Schedule — Implementation: Implement the data retention schedule developed in RA-0... | Engineering / Legal | High | [8 empty] | ▶ | ◀
RA-030 | DPDP Act — Rules Monitoring: Monitor MeitY notification of DPDP Act implementing rul... | Legal / Compliance | Medi | [8 empty] | ▶ | █ | █ | ◀
RA-031 | Access Control — Recertification: Establish a semi-annual access recertification programm... | IT Operations / CTO | Medi | [8 empty] | ▶ | ◀
RA-032 | Business Continuity: Document an ICT Continuity Plan defining Recovery Time ... | CTO / IT Operations | Medi | [10 empty] | ▶ | ◀
RA-033 | Threat Intelligence & Monitoring: Subscribe to a healthcare sector threat intelligence fe... | IT Operations / CTO | Medi | [10 empty] | ▶ | ◀
RA-034 | Certification Readiness: Following the ISMS internal audit (RA-028), address all... | CTO / ISMS Owner | Crit | [10 empty] | ▶ | ◀