## Cover
RESOLUTE COMPLIANCE ADVISORY LLP
Governance · Risk · Compliance
PRIORITISED REMEDIATION ROADMAP
ISO 27001:2022 + SOC 2 — Brightpath Technologies Pvt. Ltd.
Prepared for
Brightpath Technologies Pvt. Ltd.
IT Services · Bengaluru, India
Roadmap Period: February 2024 – February 2025
Prepared by | kay Shahbaaz
Title | GRC Analyst
Date | 28 February 2024
Field | Details
Document Title | Prioritised Remediation Roadmap
Document Ref | RCA-P1-006
Client | Brightpath Technologies Pvt. Ltd.
Source Documents | RCA-P1-002 (ISO 27001 Gap), RCA-P1-003 (SOC 2 Gap), RCA-P1-005 (Risk Register)
Frameworks | ISO 27001:2022 + SOC 2 Trust Services Criteria
Total Actions | 34
Roadmap Period | February 2024 – February 2025
Prepared by | kay Shahbaaz
Date | 28 February 2024
Version | v1.0
Classification | CONFIDENTIAL
Status | Final
CONFIDENTIALITY NOTICE — This document is prepared exclusively for Brightpath Technologies Pvt. Ltd. and may not be disclosed without prior written consent of Resolute Compliance Advisory LLP.

## Remediation Roadmap
RESOLUTE COMPLIANCE ADVISORY LLP · Remediation Roadmap · RCA-P1-006 · Brightpath Technologies Pvt. Ltd. | [9 empty] | CONFIDENTIAL
ISO 27001:2022 + SOC 2 · Assessment Period: Oct–Dec 2023 · Roadmap Period: Feb 2024 – Feb 2025 · Report Date: 28 February 2024
Action ID | Priority | Domain | Remediation Action | Framework Reference | Risk Ref | Effort | Phase | Owner | Start Month | End Month | Status
RM-001 | Critical | Governance | Appoint Information Security Officer and formally assign ISMS ownership | ISO 27001:2022 Clause 5.3 / A.5.2 | R-001 | Small (< 1 wk) | Phase 1 (Immediate) | Senior Management | Feb 2024 | Feb 2024 | Open
RM-002 | Critical | Access Control | Immediately revoke all active credentials for former employees — live risk | ISO 27001:2022 A.5.18 / A.6.5 / SOC 2 CC6.5 | R-006 | Small (< 1 wk) | Phase 1 (Immediate) | IT Manager | Feb 2024 | Feb 2024 | Open
RM-003 | Critical | Governance | Draft and obtain management sign-off on Information Security Policy | ISO 27001:2022 Clause 5.2 / A.5.1 / SOC 2 CC2.2 | R-001 | Small (< 1 wk) | Phase 1 (Immediate) | ISO / IT Manager | Feb 2024 | Mar 2024 | Open
RM-004 | Critical | Governance | Define and document ISMS scope per ISO 27001:2022 Clause 4.3 | ISO 27001:2022 Clause 4.3 | R-001 | Small (< 1 wk) | Phase 1 (Immediate) | ISO / IT Manager | Feb 2024 | Mar 2024 | Open
RM-005 | Critical | Governance | Define risk assessment methodology: criteria, likelihood/impact scale, risk appetite | ISO 27001:2022 Clause 6.1.2 / SOC 2 CC3.1 | R-003 | Small (< 1 wk) | Phase 1 (Immediate) | ISO / IT Manager | Feb 2024 | Mar 2024 | Open
RM-006 | Critical | Governance | Conduct enterprise-wide information asset inventory; assign asset owners; classify by sensitivity | ISO 27001:2022 A.5.9 / A.5.12 | R-002 | Medium (1–4 wk) | Phase 1 (Immediate) | IT Manager | Mar 2024 | Apr 2024 | Open
RM-007 | Critical | Governance | Conduct initial ISO 27001:2022 risk assessment using approved methodology; produce Risk Treatment Plan | ISO 27001:2022 Clause 6.1.2 / 6.1.3 / SOC 2 CC3.2 | R-003 | Medium (1–4 wk) | Phase 1 (Immediate) | ISO / IT Manager | Mar 2024 | May 2024 | Open
RM-008 | Critical | Access Control | Develop and implement Access Control Policy; enforce least-privilege across all AWS IAM roles | ISO 27001:2022 A.5.15 / A.5.18 / A.8.2 / SOC 2 CC6.1 / CC6.3 | R-005 | Medium (1–4 wk) | Phase 1 (Immediate) | IT Manager | Mar 2024 | Apr 2024 | Open
RM-009 | High | Access Control | Enforce MFA on all AWS accounts and administrative interfaces | ISO 27001:2022 A.8.5 / SOC 2 CC6.1 | R-008 | Small (< 1 wk) | Phase 1 (Immediate) | IT Manager | Mar 2024 | Mar 2024 | Open
RM-010 | High | People Security | Launch mandatory security awareness training for all staff; track completion | ISO 27001:2022 A.6.3 / SOC 2 CC1.4 | R-015 | Medium (1–4 wk) | Phase 1 (Immediate) | HR / IT Manager | Mar 2024 | May 2024 | Open
RM-011 | High | People Security | Implement pre-employment background screening policy; apply to all new hires from Mar 2024 | ISO 27001:2022 A.6.1 | R-016 | Small (< 1 wk) | Phase 1 (Immediate) | HR Manager | Mar 2024 | Apr 2024 | Open
RM-012 | High | People Security | Develop offboarding checklist; mandate access revocation within 24 hours of departure | ISO 27001:2022 A.6.5 / SOC 2 CC6.5 | R-006 | Small (< 1 wk) | Phase 1 (Immediate) | HR / IT Manager | Mar 2024 | Mar 2024 | Open
RM-013 | Critical | Incident Management | Develop and test Incident Response Plan; define severity levels, roles, and escalation paths | ISO 27001:2022 A.5.24 / A.5.25 / A.5.26 / SOC 2 CC7.3 / CC7.4 | R-012 | Medium (1–4 wk) | Phase 1 (Immediate) | IT Manager | Mar 2024 | May 2024 | Open
RM-014 | Critical | Vulnerability Management | Deploy vulnerability scanning (monthly cadence); define patching SLAs: Critical 72hr, High 14d, Medium 30d | ISO 27001:2022 A.8.8 / SOC 2 CC7.1 | R-018 | Medium (1–4 wk) | Phase 1 (Immediate) | IT Manager | Mar 2024 | Apr 2024 | Open
RM-015 | Critical | Third-Party Risk | Draft and execute information security addenda to all critical and high-risk supplier contracts | ISO 27001:2022 A.5.19 / A.5.20 / SOC 2 CC9.2 | R-009 | Medium (1–4 wk) | Phase 1 (Immediate) | IT Manager / Legal | Mar 2024 | May 2024 | Open
RM-016 | High | Governance | Finalise Statement of Applicability (RCA-P1-004); obtain management approval | ISO 27001:2022 Clause 6.1.3(b) | R-004 | Small (< 1 wk) | Phase 2 (Short-Term) | ISO / IT Manager | May 2024 | Jun 2024 | Open
RM-017 | High | Access Control | Implement quarterly access certification reviews; document results as audit evidence | ISO 27001:2022 A.5.18 / SOC 2 CC6.3 | R-007 | Small (< 1 wk) | Phase 2 (Short-Term) | IT Manager | May 2024 | Jun 2024 | Open
RM-018 | High | Vulnerability Management | Define and deploy network segmentation; enforce prod/dev environment separation | ISO 27001:2022 A.8.22 | R-019 | Medium (1–4 wk) | Phase 2 (Short-Term) | IT Manager | May 2024 | Jul 2024 | Open
RM-019 | High | Vulnerability Management | Define configuration baselines and hardening standards for all production systems | ISO 27001:2022 A.8.9 / SOC 2 CC6.2 | R-020 | Medium (1–4 wk) | Phase 2 (Short-Term) | IT Manager | May 2024 | Jul 2024 | Open
RM-020 | High | Incident Management | Configure AWS CloudTrail and CloudWatch alerting for defined security events | ISO 27001:2022 A.8.15 / A.8.16 / SOC 2 CC7.2 | R-013 | Small (< 1 wk) | Phase 2 (Short-Term) | IT Manager | May 2024 | Jun 2024 | Open
RM-021 | High | Third-Party Risk | Develop vendor register; conduct tiered security assessments for all critical vendors | ISO 27001:2022 A.5.19 / A.5.22 / SOC 2 CC9.2 | R-009 | Medium (1–4 wk) | Phase 2 (Short-Term) | IT Manager | May 2024 | Jul 2024 | Open
RM-022 | High | Secure Development | Adopt Secure SDLC policy; integrate OWASP Top 10 into development process | ISO 27001:2022 A.8.25 / A.8.26 / A.8.27 | R-021 | Medium (1–4 wk) | Phase 2 (Short-Term) | Development Lead | May 2024 | Aug 2024 | Open
RM-023 | High | Secure Development | Implement pre-deployment security testing (DAST/SAST) for all client-facing applications | ISO 27001:2022 A.8.29 / SOC 2 CC8.1 | R-021 | Medium (1–4 wk) | Phase 2 (Short-Term) | Development Lead | Jun 2024 | Aug 2024 | Open
RM-024 | Medium | Secure Development | Implement data masking / anonymisation for test environments; prohibit production data in test | ISO 27001:2022 A.8.11 / A.8.33 | R-023 | Small (< 1 wk) | Phase 2 (Short-Term) | Development Lead | Jun 2024 | Jul 2024 | Open
RM-025 | High | Data Protection | Develop information classification scheme; apply labels to all information assets | ISO 27001:2022 A.5.12 / A.5.13 | R-026 | Medium (1–4 wk) | Phase 2 (Short-Term) | IT Manager | May 2024 | Jul 2024 | Open
RM-026 | High | Data Protection | Implement encryption policy; enforce encryption at rest and in transit for all sensitive data | ISO 27001:2022 A.8.24 | R-026 | Medium (1–4 wk) | Phase 2 (Short-Term) | IT Manager | Jun 2024 | Aug 2024 | Open
RM-027 | High | Business Continuity | Define RTOs and RPOs for all client-facing services; document BCP and DRP | ISO 27001:2022 A.5.29 / A.5.30 / SOC 2 A1.1 / A1.3 | R-024 | Large (> 4 wk) | Phase 3 (Medium-Term) | IT Manager / Head of Ops | Jul 2024 | Oct 2024 | Open
RM-028 | High | Business Continuity | Test backup restoration; conduct BCP tabletop exercise; document test results | ISO 27001:2022 A.5.30 / SOC 2 A1.3 | R-024 | Medium (1–4 wk) | Phase 3 (Medium-Term) | IT Manager | Sep 2024 | Nov 2024 | Open
RM-029 | Medium | Governance | Implement supplier monitoring process; conduct annual reviews of critical suppliers | ISO 27001:2022 A.5.22 | R-009 | Small (< 1 wk) | Phase 3 (Medium-Term) | IT Manager | Aug 2024 | Oct 2024 | Open
RM-030 | Medium | People Security | Deploy phishing simulation programme; conduct at minimum two exercises per year | ISO 27001:2022 A.6.3 | R-015 | Small (< 1 wk) | Phase 3 (Medium-Term) | IT Manager | Jul 2024 | Sep 2024 | Open
RM-031 | Medium | Governance | Conduct ISO 27001:2022 internal audit against all Annex A controls and Clauses 4–10 | ISO 27001:2022 Clause 9.2 | R-004 | Large (> 4 wk) | Phase 3 (Medium-Term) | ISO / External Auditor | Oct 2024 | Dec 2024 | Open
RM-032 | Medium | Governance | Conduct ISO 27001:2022 Management Review per Clause 9.3; document outputs | ISO 27001:2022 Clause 9.3 | R-004 | Small (< 1 wk) | Phase 4 (Long-Term) | Senior Management | Nov 2024 | Dec 2024 | Open
RM-033 | Medium | Governance | Engage accredited Certification Body for ISO 27001:2022 Stage 1 audit | ISO 27001:2022 Certification | R-004 | Large (> 4 wk) | Phase 4 (Long-Term) | ISO / Senior Management | Dec 2024 | Feb 2025 | Open
RM-034 | Medium | Governance | Commission SOC 2 Type I readiness review with independent assessor | SOC 2 — All criteria | R-004 | Medium (1–4 wk) | Phase 4 (Long-Term) | ISO / Senior Management | Nov 2024 | Jan 2025 | Open

## Gantt Timeline
RESOLUTE COMPLIANCE ADVISORY LLP · Remediation Timeline · RCA-P1-006 · Brightpath Technologies Pvt. Ltd. |  |  |  | February 2024 → February 2025
Shaded cells indicate active remediation period for each action. Critical = Red · High = Amber · Medium = Gold · Low = Green
Action ID | Priority | Domain | Remediation Action | Feb 2024 | Mar 2024 | Apr 2024 | May 2024 | Jun 2024 | Jul 2024 | Aug 2024 | Sep 2024 | Oct 2024 | Nov 2024 | Dec 2024 | Jan 2025 | Feb 2025
RM-001 | Critical | Governance | Appoint Information Security Officer and formally assign ISMS ownership | ●
RM-002 | Critical | Access Control | Immediately revoke all active credentials for former employees — live risk | ●
RM-003 | Critical | Governance | Draft and obtain management sign-off on Information Security Policy | ● | ●
RM-004 | Critical | Governance | Define and document ISMS scope per ISO 27001:2022 Clause 4.3 | ● | ●
RM-005 | Critical | Governance | Define risk assessment methodology: criteria, likelihood/impact scale, risk... | ● | ●
RM-006 | Critical | Governance | Conduct enterprise-wide information asset inventory; assign asset owners; c... |  | ● | ●
RM-007 | Critical | Governance | Conduct initial ISO 27001:2022 risk assessment using approved methodology; ... |  | ● | ━ | ●
RM-008 | Critical | Access Control | Develop and implement Access Control Policy; enforce least-privilege across... |  | ● | ●
RM-009 | High | Access Control | Enforce MFA on all AWS accounts and administrative interfaces |  | ●
RM-010 | High | People Security | Launch mandatory security awareness training for all staff; track completio... |  | ● | ━ | ●
RM-011 | High | People Security | Implement pre-employment background screening policy; apply to all new hire... |  | ● | ●
RM-012 | High | People Security | Develop offboarding checklist; mandate access revocation within 24 hours of... |  | ●
RM-013 | Critical | Incident Management | Develop and test Incident Response Plan; define severity levels, roles, and... |  | ● | ━ | ●
RM-014 | Critical | Vulnerability Management | Deploy vulnerability scanning (monthly cadence); define patching SLAs: Crit... |  | ● | ●
RM-015 | Critical | Third-Party Risk | Draft and execute information security addenda to all critical and high-ris... |  | ● | ━ | ●
RM-016 | High | Governance | Finalise Statement of Applicability (RCA-P1-004); obtain management approva... |  |  |  | ● | ●
RM-017 | High | Access Control | Implement quarterly access certification reviews; document results as audit... |  |  |  | ● | ●
RM-018 | High | Vulnerability Management | Define and deploy network segmentation; enforce prod/dev environment separa... |  |  |  | ● | ━ | ●
RM-019 | High | Vulnerability Management | Define configuration baselines and hardening standards for all production s... |  |  |  | ● | ━ | ●
RM-020 | High | Incident Management | Configure AWS CloudTrail and CloudWatch alerting for defined security event... |  |  |  | ● | ●
RM-021 | High | Third-Party Risk | Develop vendor register; conduct tiered security assessments for all critic... |  |  |  | ● | ━ | ●
RM-022 | High | Secure Development | Adopt Secure SDLC policy; integrate OWASP Top 10 into development process |  |  |  | ● | ━ | ━ | ●
RM-023 | High | Secure Development | Implement pre-deployment security testing (DAST/SAST) for all client-facing... |  |  |  |  | ● | ━ | ●
RM-024 | Medium | Secure Development | Implement data masking / anonymisation for test environments; prohibit prod... |  |  |  |  | ● | ●
RM-025 | High | Data Protection | Develop information classification scheme; apply labels to all information ... |  |  |  | ● | ━ | ●
RM-026 | High | Data Protection | Implement encryption policy; enforce encryption at rest and in transit for ... |  |  |  |  | ● | ━ | ●
RM-027 | High | Business Continuity | Define RTOs and RPOs for all client-facing services; document BCP and DRP | [5 empty] | ● | ━ | ━ | ●
RM-028 | High | Business Continuity | Test backup restoration; conduct BCP tabletop exercise; document test resul... | [7 empty] | ● | ━ | ●
RM-029 | Medium | Governance | Implement supplier monitoring process; conduct annual reviews of critical s... | [6 empty] | ● | ━ | ●
RM-030 | Medium | People Security | Deploy phishing simulation programme; conduct at minimum two exercises per ... | [5 empty] | ● | ━ | ●
RM-031 | Medium | Governance | Conduct ISO 27001:2022 internal audit against all Annex A controls and Clau... | [8 empty] | ● | ━ | ●
RM-032 | Medium | Governance | Conduct ISO 27001:2022 Management Review per Clause 9.3; document outputs | [9 empty] | ● | ●
RM-033 | Medium | Governance | Engage accredited Certification Body for ISO 27001:2022 Stage 1 audit | [10 empty] | ● | ━ | ●
RM-034 | Medium | Governance | Commission SOC 2 Type I readiness review with independent assessor | [9 empty] | ● | ━ | ●

## Summary Dashboard
REMEDIATION ROADMAP — SUMMARY DASHBOARD
Brightpath Technologies Pvt. Ltd. · RCA-P1-006 · 28 February 2024
OVERALL ROADMAP SUMMARY
Total Actions | Critical | High | Medium | Low | Completed
34 | 11 | 16 | 7 | 0 | 0
COMPLETION RATE (update Status in Roadmap sheet as actions are completed)
Metric | Value
Overall Completion % | 0%
Critical Actions Completed | 0
High Actions Completed | 0
Medium Actions Completed | 0
ACTIONS BY PRIORITY
Priority | Total | Open | In Progress | Completed | % Complete
Critical | 11 | 11 | 0 | 0 | 0%
High | 16 | 16 | 0 | 0 | 0%
Medium | 7 | 7 | 0 | 0 | 0%
Low | 0 | 0 | 0 | 0 | 0%
ACTIONS BY DOMAIN
Domain | Total | Critical | High | Medium | Low
Governance | 12 | 6 | 1 | 5 | 0
Access Control | 4 | 2 | 2 | 0 | 0
Third-Party Risk | 2 | 1 | 1 | 0 | 0
Incident Management | 2 | 1 | 1 | 0 | 0
People Security | 4 | 0 | 3 | 1 | 0
Vulnerability Management | 3 | 1 | 2 | 0 | 0
Secure Development | 3 | 0 | 2 | 1 | 0
Business Continuity | 2 | 0 | 2 | 0 | 0
Data Protection | 2 | 0 | 2 | 0 | 0